## Project Tracking Dashboard
CYCLE TIME TRACKER
| DRAFT | ENG | PLAT | CONTRACT-PERMIT SUB | PERMIT PROCESSING | PRE-CON TOTAL
All Time | 41.0253 | 10.5857 | 9.9412 | 54.498 | 32.9155 | 90.4335
2021 and Beyond | 12.5833 | 9 | 22.6 | 22 | 16.5 | 30
2022 and Beyond | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
GOALS
| 2 | 10 | 5 | 15 | 15 | 30
*All averages based on all enties and not filtered by date at this time ***All days are calculated in workdays NOT calendar days

## Lot Specifics
| Lot Information | [5 empty] | Drafting Data |  |  |  | Engineering |  |  |  | Plat |  |  |  | Permit |  |  |  | BBP |  | Notes | Cycle times
Complete | Community | Section | Lot # | Product | Elevation | Contract Date | Assigned | Draft Deadline | Actual | Time (Min) | ENG | Eng. Sent | Planned Receipt | Actual Receipt | Plat Eng | Plat Sent | Planned Receipt2 | Actual Receipt2 | Jurisdiction | Planned Submit | Actual Submit | RECEIVED | Planned Posted Date | Actual Posted Date | Lot Notes | Draft | Engineer | Plat | Contract--Permit Submission | Permit Processing | Total Pre-Con
x | Readers Branch |  | 005 |  | 25 - Folk Victorian | 2018-05-31 | R.Arias | 2018-06-04 | 2018-09-17 | 160 |  | 9/17/2018 | 2018-06-18 | 2018-09-26 |  |  | 2018-06-18 |  |  | 2018-06-21 | 9/28/2018 |  | 1900-01-01 |  |  | 77 | 8 | 0 | 86 | -30980 | -30894
x | Readers Branch |  | 024 | Linden Terrace | 25 - Folk Victorian | 2018-05-31 | R.Arias | 2018-06-04 | 2018-09-19 | 240 |  | 9/19/2018 | 2018-06-18 | 2018-09-27 |  |  | 2018-06-18 |  |  | 2018-06-21 | 10/5/2018 | 2019-02-13 | 2019-02-14 |  | Minor door location changes (changes coming) | 79 | 7 | 0 | 91 | 94 | 185
x | Readers Branch |  | 033 | Linden Terrace | 25 - Folk Victorian | 2018-05-31 | R.Arias | 2018-06-04 | 2018-09-19 | 160 |  | 9/19/2018 | 2018-06-18 | 2018-09-27 |  |  | 2018-06-18 |  |  | 2018-06-21 | 9/28/2018 | 2019-02-13 | 2019-02-14 |  | Window location changes | 79 | 7 | 0 | 86 | 99 | 185
x | Readers Branch |  | 034 | Hartford Terrace | 10 - Traditional | 2018-06-04 | R.Arias | 2018-06-06 | 2018-09-19 | 200 |  | 9/19/2018 | 2018-06-20 | 2018-09-26 |  |  | 2018-06-20 |  |  | 2018-06-25 | 10/12/2018 |  | 1900-01-01 |  | Bay window added, structural received 10/8/18, centering windows based on final customer changes (Ad #8) | 77 | 6 | 0 | 94 | -30990 | -30896
x | Readers Branch |  | 009 | Hartford Terrace | 40 - European | 2018-06-04 | R.Arias | 2018-06-06 | 2018-11-21 | 300 |  | 10/4/2018 (11/21/2018) | 2018-06-20 | 2018-10-15 |  |  | 2018-06-20 |  |  | 2018-06-25 | 10/19/2018 | 2019-03-11 | 2019-03-12 |  | AT STRUCTURAL -NEEDS RESUBMISSION TO COUNTY (Shortened lot) | 122 | #VALUE! | 0 | 99 | 102 | 201
x | Readers Branch |  | 012 | Hartford Terrace | 30 - Craftsman | 2018-07-13 | R.Arias | 2018-07-17 | 2018-09-27 | 180 |  | 9/27/2018 | 2018-07-31 | 2018-10-05 |  |  | 2018-07-31 |  |  | 2018-08-03 | 10/12/2018 | 2019-02-01 | 2019-02-04 |  | No Changes | 54 | 7 | 0 | 65 | 81 | 146
x | Readers Branch |  | 028 | Linden Terrace | 10 - Traditional | 2018-07-24 | R.Arias | 2018-07-26 | 2018-09-26 | 140 |  | 9/26/2018 | 2018-08-09 | 10/3/2018 (10/19/2018) |  |  | 2018-08-09 |  |  | 2018-08-14 | 10/26/2018 | 2019-02-15 | 2019-02-18 |  | twin window on 11/26/2018, | 46 | #VALUE! | 0 | 68 | 81 | 149
x | Readers Branch |  | 019 | Linden Terrace | 10 - Traditional | 2018-07-31 | R.Arias | 2018-08-02 | 2018-09-25 | 120 |  | 9/25/2018 02/22/2019 | 2018-08-16 | 2018-10-03 |  |  | 2018-08-16 |  |  | 2018-08-21 | 10/26/2018 |  | 1900-01-01 |  | Needs to go back to structure then back to county | 40 | #VALUE! | 0 | 63 | -31000 | -30937
x | Readers Branch |  | 026 | Linden Terrace | 10 - Traditional | 2018-07-31 | R.Arias | 2018-08-02 | 2018-10-05 | 100 |  | 10/5/2018 02/18/2019 | 2018-08-16 | 10/10/2018 03/01/2019 |  |  | 2018-08-16 |  |  | 2018-08-21 | 10/12/2018 | 2019-02-15 | 2019-02-18 |  | Old elevation conversion, needs resubmission | 48 | #VALUE! | 0 | 53 | 91 | 144
x | Readers Branch |  | 016 | Linden Terrace | 30 - Craftsman | 2018-08-10 | R.Arias | 2018-08-14 | 2018-10-05 | 100 |  | 10/5/2018 04/03/2019 | 2018-08-28 | 2018-10-10 |  |  | 2018-08-28 |  |  | 2018-08-31 |  | 2019-02-05 | 2019-02-06 |  | Never went to county due to elevation change (being redrawn) | 40 | #VALUE! | 0 | -30946 | 31072 | 128
x | Readers Branch |  | 013 | Hartford Terrace | 40 - European | 2018-08-14 | R.Arias | 2018-08-16 | 2018-10-01 | 510 |  | 10/01/2018 | 2018-08-30 | 2018-10-16 |  |  | 2018-08-30 |  |  | 2018-09-04 | 10/19/2018 | 2019-02-06 | 2019-02-07 |  | NEED RESUBMISSION, Changes coming again, already at engineering again (11/16/2018) | 34 | 12 | 0 | 48 | 79 | 127
x | Readers Branch |  | 021 | Hartford Terrace | 10 - Traditional | 2018-08-14 | R.Arias | 2018-08-16 | 2018-10-09 | 80 |  | 10/9/2018 | 2018-08-30 | 2018-10-15 |  |  | 2018-08-30 |  |  | 2018-09-04 | 10/19/2018 | 2019-03-06 | 2019-03-07 |  | No changes, responded to county notes | 40 | 5 | 0 | 48 | 99 | 147
x | Readers Branch |  | 035 | Linden Terrace | 10 - Traditional | 2018-10-30 | R.Arias | 2018-11-01 | 2019-01-29 | 160 |  | 02/01/2019 | 2018-11-15 | 2019-02-13 |  |  | 2018-11-15 |  |  | 2018-11-20 | 02/14/2019 | 2019-04-30 | 2019-05-01 |  |  | 65 | 9 | 0 | 77 | 54 | 131
x | Readers Branch |  | 015 | Linden Terrace | 25 - Folk Victorian | 2018-11-21 | Y.Wang | 2018-11-23 | 2019-01-29 | 200 |  | 02/01/2019 | 2018-12-07 | 2019-02-11 |  |  | 2018-12-07 |  |  | 2018-12-12 | 02/11/2019 | 2019-04-30 | 2019-05-01 |  |  | 49 | 7 | 0 | 58 | 57 | 115
x | Readers Branch |  | 020 | Belmont Terrace | 10 - Traditional | 2018-11-28 | J.Cobb | 2018-11-30 | 2019-01-25 | 300 |  | 02/01/2019 | 2018-12-14 | 2019-02-13 |  |  | 2018-12-14 |  |  | 2018-12-19 | 02/14/2019 | 2019-04-30 | 2019-05-01 |  |  | 42 | 9 | 0 | 56 | 54 | 110
x | Readers Branch |  | 018 | Linden Terrace | 30 - Craftsman | 2018-12-13 | C.Zobel | 2018-12-17 | 2019-01-30 | 390 |  | 02/01/2019 | 2018-12-31 | 2019-02-13 |  |  | 2018-12-31 |  |  | 2019-01-03 | 02/18/2019 | 2019-05-03 | 2019-05-06 |  |  | 34 | 9 | 0 | 47 | 55 | 102
x | GreenGate |  | 075 | Rowland | GR - D - 2 - R | 2019-01-16 | Y.Wang | 2019-01-18 | 2018-11-16 | 720 |  | 12/10/2018 | 2019-02-01 | 2018-12-31 |  |  | 2019-02-01 |  |  | 2019-02-06 | 01/22/2019 | 2019-02-07 | 2019-02-08 |  |  | -45 | 16 | 0 | 4 | 13 | 17
x | Readers Branch |  | 032 | Linden Terrace | 30 - Craftsman | 2019-01-21 | C.Zobel | 2019-01-23 | 2019-02-07 | 720 |  | 03/28/2019 | 2019-02-06 | 2019-04-09 |  |  | 2019-02-06 |  |  | 2019-02-11 | 04/10/209 | 2019-05-16 | 2019-05-17 |  |  | 13 | 9 | 0 | #VALUE! | #VALUE! | 84
x | GreenGate |  | 076 | Park | QA - D - 2 - R | 2019-01-28 | Y.Wang | 2019-01-30 | 2018-11-16 | 720 |  | 12/10/2018 | 2019-02-13 | 2018-12-31 |  |  | 2019-02-13 |  |  | 2019-02-18 | 01/22/2019 | 2019-02-07 | 2019-02-08 |  |  | -53 | 16 | 0 | -6 | 13 | 9
x | Harpers Mill |  | 004 | Linden Terrace | 30 - Craftsman | 2019-01-31 | R.Arias | 2019-02-04 | 2019-02-13 | 180 |  | 02/14/2019 | 2019-02-18 |  |  |  | 2019-02-18 |  |  | 2019-02-21 |  |  | 1900-01-01 |  |  | 9 | -31079 | 0 | -31070 | 0 | -31069
x | Readers Branch |  | 039 | Belmont |  | 02/05/2019 | J.Cobb | 2019-02-07 | 2019-03-05 | 480 |  | 04/05/2019 | 2019-02-21 | 04/10/2019 |  |  | 2019-02-21 |  |  | 2019-02-26 | 04/12/2019 | 05/16/2019 | 2019-05-17 |  |  | 20 | 4 | 0 | 48 | 25 | 73
x | Readers Branch |  | 006 | Linden Terrace | 30 - Craftsman | 2019-02-11 | C.Zobel | 2019-02-13 | 2019-03-07 | 360 |  | 03/11/2019 | 2019-02-27 | 2019-03-25 |  |  | 2019-02-27 |  |  | 2019-03-04 | 04/01/2019 | 2019-05-31 | 2019-06-03 |  |  | 18 | 11 | 0 | 35 | 45 | 80
x | Lauradell | 1 | 72 | Beverly | 10 - Traditional | 02/11/2019 | C.Zobel | 2019-02-13 | 2019-10-09 | 150 |  | 10/10/2019 | 2019-02-27 | 10/15/2019 |  |  | 2019-02-27 |  |  | 2019-03-04 | 10/16/2019 | 02/21/2020 | 2020-02-24 |  |  | 172 | 4 | 0 | 177 | 93 | 270
x | Parkside Village | 4 | 56 | Corvallis | 40 - European | 02/25/2019 | C.Zobel | 2019-02-27 | 2020-02-12 | 270 |  | 02/14/2020 | 2019-03-13 | 02/18/2020 |  |  | 2019-03-13 |  |  | 2019-03-18 | 04/14/2020 | 05/26/2020 | 2020-05-27 |  |  | 252 | 3 | 0 | 296 | 31 | 327
x | Readers Branch | 2 | 054 | Hartford Terrace | 30 - Craftsman | 02/27/2019 | C.Zobel | 2019-03-01 | 2019-08-20 | 300 |  | 8/26/2019 | 2019-03-15 | 9/4/2019 |  |  | 2019-03-15 |  |  | 2019-03-20 | 9/4/2019 | 11/22/2019 | 2019-11-25 |  |  | 124 | 8 | 0 | 135 | 58 | 193
x | Parkside Village | 4 | 52 | Carlisle | 15 - Arts & Crafts | 02/28/2019 | C.Zobel | 2019-03-04 | 2020-02-11 | 270 |  | 02/11/2020 | 2019-03-18 | 02/12/2020 |  |  | 2019-03-18 |  |  | 2019-03-21 | 04/14/2020 | 05/26/2020 | 2020-05-27 |  |  | 248 | 2 | 0 | 293 | 31 | 324
x | Lauradell | 1 | 97 | Corvallis | 30 - Craftsman | 03/16/2019 | C.Zobel | 2019-03-19 | 2019-10-10 | 120 |  | 10/14/2019 | 2019-04-02 | 10/18/2019 |  |  | 2019-04-02 |  |  | 2019-04-05 | 10/18/2019 | 02/21/2020 | 2020-02-24 |  |  | 148 | 5 | 0 | 154 | 91 | 245
x | Parkside Village | 4 | 11 | Carlisle | 15 - Arts & Crafts | 03/16/2019 | C.Zobel | 2019-03-19 | 2020-02-19 | 180 |  | 02/20/2020 | 2019-04-02 | 02/25/2020 |  |  | 2019-04-02 |  |  | 2019-04-05 | 04/17/2020 | 05/28/2020 | 2020-05-29 |  |  | 242 | 4 | 0 | 284 | 30 | 314
x | Readers Branch |  | 011 | Belmont Terrace | 15 - Arts & Crafts | 03/31/2019 | C.Zobel | 2019-04-02 | 2019-05-17 | 270 |  | 05/21/2019 | 2019-04-16 | 05/31/2019 |  |  | 2019-04-16 |  |  | 2019-04-19 | 06/05/2019 | 07/15/2019 | 2019-07-16 |  |  | 34 | 9 | 0 | 47 | 29 | 76
x | Readers Branch | 2 | 036 | Hartford Terrace | 10 - Traditional | 04/13/2019 | C.Zobel | 2019-04-16 | 2019-08-21 | 240 |  | 08/27/2019 | 2019-04-30 | 9/6/2019 |  |  | 2019-04-30 |  |  | 2019-05-03 | 9/6/2019 | 11/22/2019 | 2019-11-25 |  |  | 92 | 9 | 0 | 104 | 56 | 160
x | Lauradell | 1 | 81 | Corvallis | 20 - Colonial | 04/15/2019 | C.Zobel | 2019-04-17 | 2019-10-11 | 190 |  | 10/14/2019 | 2019-05-01 | 10/18/2019 |  |  | 2019-05-01 |  |  | 2019-05-06 | 10/18/2019 | 02/21/2020 | 2020-02-24 |  |  | 129 | 5 | 0 | 134 | 91 | 225
x | GreenGate |  | 091 | Malvern | QA - D - 1 - F | 2019-04-23 | Y.Wang | 2019-04-25 | 2019-03-15 | 600 |  | 03/15/2019 | 2019-05-09 | 03/29/2019 |  |  | 2019-05-09 |  |  | 2019-05-14 | 04/02/2019 | 5/9/2019 | 2019-05-10 |  |  | -29 | 11 | 0 | -17 | 28 | 13
x | Readers Branch | 2 | 051 | Linden Terrace | 30 - Craftsman | 04/25/2019 | C.Zobel | 2019-04-29 | 2019-08-29 | 330 |  | 08/30/2019 | 2019-05-13 | 09/10/2019 |  |  | 2019-05-13 |  |  | 2019-05-16 | 09/10/2019 | 12/2/2019 | 2019-12-03 |  |  | 90 | 8 | 0 | 98 | 60 | 158
x | Readers Branch |  | 027 | Linden Terrace | 30 - Craftsman | 04/30/2019 | C.Zobel | 2019-05-02 | 2019-05-23 | 840 |  | 05/29/2019 | 2019-05-16 | 06/12/2019 |  |  | 2019-05-16 |  |  | 2019-05-21 | 06/14/2019 | 07/15/2019 | 2019-07-16 |  |  | 17 | 11 | 0 | 33 | 22 | 55
x | Readers Branch |  | 017 | Belmont Terrace | 15 - Arts & Crafts | 05/06/2019 | C.Zobel | 2019-05-08 | 2019-05-28 | 270 |  | 05/29/2019 | 2019-05-22 | 06/14/2019 |  |  | 2019-05-22 |  |  | 2019-05-27 | 06/14/2019 | 06/28/2019 | 2019-07-01 |  |  | 16 | 13 | 0 | 29 | 11 | 40
x | Parkside Village | 4 | 8 | Fulton | BSE - Arts & Crafts | 05/06/2019 | C.Zobel | 2019-05-08 | 2020-02-17 | 120 |  | 02/18/2020 | 2019-05-22 | 02/20/2020 |  |  | 2019-05-22 |  |  | 2019-05-27 | 04/17/2020 | 05/26/2020 | 2020-05-27 |  |  | 205 | 3 | 0 | 249 | 28 | 277
x | Readers Branch | 2 | 056 | Linden Terrace | 10 - Traditional | 05/09/2019 | C.Zobel | 2019-05-13 | 2019-09-05 | 300 |  | 09/10/2019 | 2019-05-27 | 09/19/2019 |  |  | 2019-05-27 |  |  | 2019-05-30 | 09/19/2019 | 12/02/2019 | 2019-12-03 |  |  | 85 | 8 | 0 | 95 | 53 | 148
x | Readers Branch | 2 | 015 | Linden Terrace | 25 - Folk Victorian | 06/07/2019 | C.Zobel | 2019-06-11 | 2019-08-22 | 300 |  | 08/29/2019 | 2019-06-25 | 9/6/2019 |  |  | 2019-06-25 |  |  | 2019-06-28 | 9/9/2019 | 12/10/2019 | 2019-12-11 |  |  | 54 | 7 | 0 | 66 | 67 | 133
x | Readers Branch | 2 | 46 | Belmont | 30 - Craftsman | 06/08/2019 | C.Zobel | 2019-06-11 | 2019-10-02 | 200 |  | 10/03/2019 | 2019-06-25 | 10/09/2019 |  |  | 2019-06-25 |  |  | 2019-06-28 | 10/24/2019 | 12/11/2019 | 2019-12-12 |  |  | 82 | 5 | 0 | 98 | 35 | 133
x | Harpers Mill |  | 006 | Linden Terrace | 10 - Traditional | 06/18/2019 | C.Zobel | 2019-06-20 | 2019-07-05 | 100 |  | 07/05/2019 | 2019-07-04 | 07/16/2019 |  |  | 2019-07-04 |  |  | 2019-07-09 | 07/16/2019 | 08/27/2019 | 2019-08-28 |  |  | 13 | 8 | 0 | 20 | 31 | 51
x | GreenGate |  | 093 | Park | QA - A - 1 - F | 2019-06-24 | Y.Wang | 2019-06-26 | 2019-03-15 | 600 |  | 03/15/2019 | 2019-07-10 | 03/29/2019 |  |  | 2019-07-10 |  |  | 2019-07-15 | 04/02/2019 | 5/9/2019 | 2019-05-10 |  |  | -73 | 11 | 0 | -61 | 28 | -33
x | Readers Branch | 2 | 30 | Belmont | 10 - Traditional | 06/26/2019 | C.Zobel | 2019-06-28 | 2019-10-03 | 100 |  | 10/03/2019 | 2019-07-12 | 10/25/2019 |  |  | 2019-07-12 |  |  | 2019-07-17 | 10/28/2019 | 12/12/2019 | 2019-12-13 |  |  | 71 | 17 | 0 | 88 | 34 | 122
x | Lauradell | 1 | 85 | Beverly | 30 - Craftsman | 06/27/2019 | C.Zobel | 2019-07-01 | 2019-10-16 | 110 |  | 10/16/2019 | 2019-07-15 | 10/22/2019 |  |  | 2019-07-15 |  |  | 2019-07-18 | 10/23/2019 | 02/21/2020 | 2020-02-24 |  |  | 79 | 5 | 0 | 84 | 88 | 172
x | Lauradell | 1 | 110 | Beverly | 10 - Traditional | 06/30/2019 | C.Zobel | 2019-07-02 | 2019-10-14 | 100 |  | 10/16/2019 | 2019-07-16 | 10/22/2019 |  |  | 2019-07-16 |  |  | 2019-07-19 | 10/23/2019 | 03/18/2020 | 2020-03-19 |  |  | 75 | 5 | 0 | 82 | 106 | 188
x | GreenGate |  | 089 | Malvern | GR - C - 1 - F | 2019-07-03 | Y.Wang | 2019-07-05 | 2019-03-15 | 600 |  | 03/15/2019 | 2019-07-19 | 03/29/2019 |  |  | 2019-07-19 |  |  | 2019-07-24 | 04/02/2019 | 5/9/2019 | 2019-05-10 |  |  | -80 | 11 | 0 | -68 | 28 | -40
x | Parkside Village | 4 | 7 | Corvallis | 20 - Colonial | 07/06/2019 | Y.Wang | 2019-07-09 | 2020-02-26 | 250 |  | 02/26/2020 | 2019-07-23 | 02/28/2020 |  |  | 2019-07-23 |  |  | 2019-07-26 |  |  | 1900-01-01 |  |  | 167 | 3 | 0 | -31181 | 0 | -31180
x | Lauradell | 1 | 106 | Beverly | 10 - Traditional | 07/09/2019 | C.Zobel | 2019-07-11 | 2019-10-30 | 120 |  | 11/12/2019 | 2019-07-25 | 11/14/2019 |  |  | 2019-07-25 |  |  | 2019-07-30 | 11/19/2019 | 03/18/2020 | 2020-03-19 |  |  | 81 | 3 | 0 | 95 | 87 | 182
x | Parkside Village | 4 | 6 | Corvallis | 10 - Traditional | 07/12/2019 | Y.Wang | 2019-07-16 | 2020-02-25 | 240 |  | 02/25/2020 | 2019-07-30 | 02/28/2020 |  |  | 2019-07-30 |  |  | 2019-08-02 |  |  | 1900-01-01 |  |  | 162 | 4 | 0 | -31186 | 0 | -31185
x | Readers Branch | 2 | 053 | Linden Terrace | 30 - Craftsman | 07/20/2019 | C.Zobel | 2019-07-23 | 2019-08-30 | 240 |  | 09/03/2019 | 2019-08-06 | 09/13/2019 |  |  | 2019-08-06 |  |  | 2019-08-09 | 09/13/2019 | 12/30/2019 | 2019-12-31 |  |  | 29 | 9 | 0 | 39 | 77 | 116
x | GreenGate |  | 077 | Rowland | GE - A - 2 - R | 2019-07-22 | Y.Wang | 2019-07-24 | 2018-11-16 | 720 |  | 12/10/2018 | 2019-08-07 | 2018-12-31 |  |  | 2019-08-07 |  |  | 2019-08-12 | 01/22/2019 | 2019-02-07 | 2019-02-08 |  |  | -178 | 16 | 0 | -131 | 13 | -118
x | Parkside Village | 4 | 55 | Linden III | 30 - Craftsman | 07/22/2019 | C.Zobel | 2019-07-24 | 2020-04-02 | 240 |  | 04/02/2020 | 2019-08-07 | 04/08/2020 |  |  | 2019-08-07 |  |  | 2019-08-12 | 04/09/2020 | 06/01/2020 | 2020-06-02 |  |  | 183 | 5 | 0 | 188 | 38 | 226
x | Parkside Village | 4 | 9 | Carlisle | 15 - Arts & Crafts | 07/24/2019 | C.Zobel | 2019-07-26 | 2020-04-06 | 285 |  | 04/07/2020 | 2019-08-09 | 04/11/2020 |  |  | 2019-08-09 |  |  | 2019-08-14 | 04/21/2020 | 05/28/2020 | 2020-05-29 |  |  | 183 | 4 | 0 | 194 | 28 | 222
x | Parkside Village | 4 | 17 | Corvallis | 10 - Traditional | 07/27/2019 | Y.Wang | 2019-07-30 | 2020-03-06 | 320 |  | 03/06/2020 | 2019-08-13 |  |  |  | 2019-08-13 |  |  | 2019-08-16 |  |  | 1900-01-01 |  |  | 159 | -31355 | 0 | -31196 | 0 | -31195
x | Readers Branch | 2 | 055 | Linden Terrace | 25 - Folk Victorian | 07/28/2019 | C.Zobel | 2019-07-30 | 2019-09-10 | 150 |  | 09/10/2019 | 2019-08-13 | 09/20/2019 |  |  | 2019-08-13 |  |  | 2019-08-16 | 09/23/2019 | 01/06/2020 | 2020-01-07 |  |  | 31 | 9 | 0 | 40 | 76 | 116
x | Parkside Village | 4 | 5 | Linden III | 30 - Craftsman | 07/28/2019 | Y.Wang | 2019-07-30 | 2020-04-07 | 300 |  | 04/07/2020 | 2019-08-13 | 04/11/2020 |  |  | 2019-08-13 |  |  | 2019-08-16 | 04/21/2020 | 05/28/2020 | 2020-05-29 |  |  | 181 | 4 | 0 | 191 | 28 | 219
x | Harpers Mill |  | 008 | Belmont | 15 - Arts & Crafts | 07/30/2019 | C.Zobel | 2019-08-01 | 2019-08-07 | 270 |  | 08/19/2019 | 2019-08-15 | 08/21/2019 |  |  | 2019-08-15 |  |  | 2019-08-20 | 08/21/2019 | 9/10/2019 | 2019-09-11 |  |  | 6 | 3 | 0 | 16 | 15 | 31
x | Readers Branch | 2 | 003 | Linden Terrace | 25 - Folk Victorian | 08/03/2019 | R.Arias | 2019-08-06 | 2019-08-23 |  |  | 09/03/2019 | 2019-08-20 | 09/12/2019 |  |  | 2019-08-20 |  |  | 2019-08-23 | 09/19/2019 | 12/30/2019 | 2019-12-31 |  | Addendum received 9/12/2019. Needs reengineering. Updated enginering received 9/19/2019. | 14 | 8 | 0 | 33 | 73 | 106
x | Readers Branch | 2 | 031 | Corvallis | 20 - Colonial | 08/03/2019 | C.Zobel | 2019-08-06 | 2019-11-05 | 210 |  | 11/21/2019 | 2019-08-20 | 12/10/2019 |  |  | 2019-08-20 |  |  | 2019-08-23 | 12/10/2019 | 01/27/2020 | 2020-01-28 |  |  | 66 | 14 | 0 | 91 | 35 | 126
x | Parkside Village | 4 | 14 | Linden III | 10 - Traditional | 08/06/2019 | Y.Wang | 2019-08-08 | 2020-04-09 | 300 |  | 04/09/2020 | 2019-08-22 | 04/16/2020 |  |  | 2019-08-22 |  |  | 2019-08-27 | 04/24/2020 | 06/01/2020 | 2020-06-02 |  |  | 177 | 6 | 0 | 188 | 27 | 215
x | Lauradell | 1 | 99 | Beverly | 30 - Craftsman | 08/16/2019 | C.Zobel | 2019-08-20 | 2019-10-30 | 165 |  | 10/31/2019 | 2019-09-03 | 11/04/2019 |  |  | 2019-09-03 |  |  | 2019-09-06 | 11/04/2019 | 03/18/2020 | 2020-03-19 |  |  | 53 | 3 | 0 | 56 | 98 | 154
x | Readers Branch | 2 | 028 | Belmont | 15 - Arts & Crafts | 08/28/2019 | Y.Wang | 2019-08-30 | 2019-11-11 | 320 |  | 12/04/2019 | 2019-09-13 | 12/11/2019 |  |  | 2019-09-13 |  |  | 2019-09-18 |  | 01/27/2020 | 2020-01-28 |  |  | 53 | 6 | 0 | -31219 | 31326 | 109
x | Lauradell | 1 | 82 | Helena | 30 - Craftsman | 08/29/2019 | C.Zobel | 2019-09-02 | 2019-11-07 | 245 |  | 11/12/2019 | 2019-09-16 | 11/15/2019 |  |  | 2019-09-16 |  |  | 2019-09-19 | 11/19/2019 | 03/18/2020 | 2020-03-19 |  |  | 50 | 4 | 0 | 58 | 87 | 145
x | Readers Branch | 2 | 29 | Corvallis | 30 - Craftsman | 08/29/2019 | C.Zobel | 2019-09-02 | 2019-11-20 | 255 |  | 11/21/2019 | 2019-09-16 | 12/03/2019 |  |  | 2019-09-16 |  |  | 2019-09-19 | 12/04/2019 | 01/27/2020 | 2020-01-28 |  |  | 59 | 9 | 0 | 69 | 39 | 108
x | Harpers Mill | 4 | 16 | Corvallis | 40 - European | 08/29/2019 | C.Zobel | 2019-09-02 | 2019-12-10 | 285 |  | 12/19/2019 | 2019-09-16 | 12/27/2019 |  |  | 2019-09-16 |  |  | 2019-09-19 | 12/30/2019 | 01/24/2020 | 2020-01-27 |  |  | 73 | 7 | 0 | 87 | 20 | 107
x | Readers Branch | 2 | 014 | Linden Terrace | 30 - Craftsman | 08/30/2019 | C.Zobel | 2019-09-03 | 2019-11-05 | 330 |  | 11/12/2019 | 2019-09-17 | 11/19/2019 |  |  | 2019-09-17 |  |  | 2019-09-20 | 11/19/2019 | 12/23/2019 | 2019-12-24 |  |  | 47 | 6 | 0 | 57 | 25 | 82
x | Harpers Mill | 4 | 25 | Linden Terrace | 30 - Craftsman | 09/07/2019 | C.Zobel | 2019-09-10 | 2019-12-23 | 260 |  | 12/30/2019 | 2019-09-24 | 01/07/2020 |  |  | 2019-09-24 |  |  | 2019-09-27 | 01/07/2020 | 03/23/2020 | 2020-03-24 |  | basement screened porch | 75 | 7 | 0 | 86 | 55 | 141
x | Readers Branch | 2 | 13 | Linden Terrace | 25 - Folk Victorian | 09/16/2019 | C.Zobel | 2019-09-18 | 2019-12-10 | 260 |  | 12/23/2019 | 2019-10-02 | 12/26/2019 |  |  | 2019-10-02 |  |  | 2019-10-07 | 12/30/2019 | 02/03/2020 | 2020-02-04 |  |  | 61 | 4 | 0 | 75 | 26 | 101
x | Harpers Mill | 2 | 30 | Corvallis | 10 - Traditional | 09/20/2019 | C.Zobel | 2019-09-24 | 2019-10-01 | 390 |  | 10/03/2019 | 2019-10-08 | 10/09/2019 |  |  | 2019-10-08 |  |  | 2019-10-11 | 10/14/2019 | 10/28/2019 | 2019-10-29 |  |  | 7 | 5 | 0 | 16 | 11 | 27
x | Readers Branch | 2 | 2 | Corvallis | 40 - European | 09/22/2019 | C.Zobel | 2019-09-24 | 2020-01-06 | 360 |  | 01/07/2020 | 2019-10-08 | 01/16/2020 |  |  | 2019-10-08 |  |  | 2019-10-11 | 01/20/2020 | 02/03/2020 | 2020-02-04 |  |  | 75 | 8 | 0 | 85 | 11 | 96
x | Readers Branch | 2 | 35 | Belmont Terrace | 10 - Traditional | 09/23/2019 | R.Arias | 2019-09-25 | 2020-01-13 | 240 |  | 01/14/2020 | 2019-10-09 | 01/22/2020 |  |  | 2019-10-09 |  |  | 2019-10-14 | 01/23/2020 | 02/11/2020 | 2020-02-12 |  |  | 80 | 7 | 0 | 88 | 14 | 102
x | Lauradell | 1 | 96 | Raleigh | 40 - Arts & Crafts B | 09/26/2019 | C.Zobel | 2019-09-30 | 2019-11-06 | 150 |  | 11/06/2019 | 2019-10-14 | 11/11/2019 |  |  | 2019-10-14 |  |  | 2019-10-17 | 11/13/2019 | 03/18/2020 | 2020-03-19 |  |  | 29 | 4 | 0 | 34 | 91 | 125
x | Harpers Mill | 4 | 20 | Carlisle | 10 - Traditional | 09/28/2019 | C.Zobel | 2019-10-01 | 2019-12-18 | 400 |  | 12/23/2019 | 2019-10-15 | 12/30/2019 |  |  | 2019-10-15 |  |  | 2019-10-18 | 12/31/2019 | 02/03/2020 | 2020-02-04 |  |  | 57 | 6 | 0 | 66 | 25 | 91
x | Readers Branch | 2 | 10 | Linden III | 30 - Craftsman | 09/30/2019 | C.Zobel | 2019-10-02 | 2020-01-07 | 240 |  | 01/08/2020 | 2019-10-16 | 01/17/2020 |  |  | 2019-10-16 |  |  | 2019-10-21 | 01/20/2020 | 02/11/2020 | 2020-02-12 |  |  | 71 | 8 | 0 | 80 | 17 | 97
x | Readers Branch | 2 | 38 | Hartford II | B - Craftsman | 09/30/2019 | C.Zobel | 2019-10-02 | 2020-01-10 | 210 |  | 01/13/2020 | 2019-10-16 | 01/17/2020 |  |  | 2019-10-16 |  |  | 2019-10-21 | 01/21/2020 | 02/27/2020 | 2020-02-28 |  |  | 74 | 5 | 0 | 81 | 28 | 109
x | Parkside Village | 4 | 21 | Linden III | 10 - Traditional | 09/30/2019 | Y.Wang | 2019-10-02 | 2020-04-10 | 300 |  | 04/10/2020 | 2019-10-16 | 04/14/2020 |  |  | 2019-10-16 |  |  | 2019-10-21 | 04/24/2020 | 06/01/2020 | 2020-06-02 |  |  | 139 | 3 | 0 | 149 | 27 | 176
x | Harpers Mill | 4 | 32 | Corvallis | 40 - European | 10/03/2019 | C.Zobel | 2019-10-07 | 2019-12-31 | 190 |  | 01/02/2020 | 2019-10-21 | 01/09/2020 |  |  | 2019-10-21 |  |  | 2019-10-24 | 01/13/2020 | 02/04/2020 | 2020-02-05 |  |  | 63 | 6 | 0 | 72 | 17 | 89
x | Lauradell | 1 | 84 | Grayson | 10 - Traditional | 10/04/2019 | C.Zobel | 2019-10-08 | 2019-11-12 | 300 |  | 12/06/2019 | 2019-10-22 | 12/12/2019 |  |  | 2019-10-22 |  |  | 2019-10-25 | 01/16/2020 | 02/21/2020 | 2020-02-24 |  |  | 27 | 5 | 0 | 74 | 27 | 101
x | Readers Branch | 2 | 22 | Belmont | 10 - Traditional | 10/17/2019 | C.Zobel | 2019-10-21 | 2020-01-14 | 180 |  | 01/15/2020 | 2019-11-04 | 01/17/2020 |  |  | 2019-11-04 |  |  | 2019-11-07 | 01/21/2020 | 02/19/2020 | 2020-02-20 |  |  | 63 | 3 | 0 | 68 | 22 | 90
x | Cypress Creek | 7B | 355 | Hartford II | BSE - Arts & Crafts | 10/19/2019 | C.Zobel | 2019-10-22 | 2019-11-19 | 255 |  | 11/21/2019 | 2019-11-05 | 12/13/2019 |  |  | 2019-11-05 |  |  | 2019-11-08 | 12/16/2019 | 03/02/2020 | 2020-03-03 |  |  | 21 | 17 | 0 | 40 | 56 | 96
x | Readers Branch | 2 | 34 | Linden Terrace | 25 - Folk Victorian | 10/19/2019 | C.Zobel | 2019-10-22 | 2020-01-08 | 300 |  | 01/10/2020 | 2019-11-05 | 01/17/2020 |  |  | 2019-11-05 |  |  | 2019-11-08 | 01/21/2020 | 02/07/2020 | 2020-02-10 |  | garage extension - side | 57 | 6 | 0 | 66 | 14 | 80
x | Lauradell | 1 | 83 | Helena | 10 - Traditional | 10/19/2019 | C.Zobel | 2019-10-22 | 2020-01-31 | 120 |  | 02/04/2020 | 2019-11-05 | 02/07/2020 |  |  | 2019-11-05 |  |  | 2019-11-08 | 02/18/2020 | 03/31/2020 | 2020-04-01 |  |  | 74 | 4 | 0 | 86 | 31 | 117
x | Cypress Creek | 7B | 353 | Linden III | 30 - Craftsman | 10/20/2019 | C.Zobel | 2019-10-22 | 2019-11-26 | 780 |  | 12/17/2019 | 2019-11-05 | 12/27/2019 |  |  | 2019-11-05 |  |  | 2019-11-08 | 12/30/2019 | 03/19/2020 | 2020-03-20 |  | additional detached single garage | 26 | 9 | 0 | 50 | 59 | 109
x | Harpers Mill | 4 | 35 | Corvallis | 40 - European | 10/26/2019 | C.Zobel | 2019-10-29 | 2020-01-23 | 135 |  | 01/24/2020 | 2019-11-12 | 01/29/2020 |  |  | 2019-11-12 |  |  | 2019-11-15 | 02/05/2020 | 03/09/2020 | 2020-03-10 |  |  | 63 | 4 | 0 | 72 | 24 | 96
x | Harpers Mill | 4 | 33 | Hartford II | BSE - Arts & Crafts | 10/31/2019 | C.Zobel | 2019-11-04 | 2020-01-03 | 195 |  | 01/03/2020 | 2019-11-18 | 01/14/2020 |  |  | 2019-11-18 |  |  | 2019-11-21 | 01/21/2020 | 02/04/2020 | 2020-02-05 |  |  | 46 | 8 | 0 | 58 | 11 | 69
x | Readers Branch | 2 | 16 | Linden Terrace | 30 - Craftsman | 10/31/2019 | C.Zobel | 2019-11-04 | 2020-01-13 | 120 |  | 01/14/2020 | 2019-11-18 | 01/22/2020 |  |  | 2019-11-18 |  |  | 2019-11-21 | 01/23/2020 | 02/07/2020 | 2020-02-10 |  |  | 52 | 7 | 0 | 60 | 12 | 72
x | Parkside Village | 4 | 58 | Corvallis | 40 - European | 11/15/2019 | Y.Wang | 2019-11-19 | 2020-04-17 | 300 |  | 04/17/2020 | 2019-12-03 | 04/20/2020 |  |  | 2019-12-03 |  |  | 2019-12-06 | 04/25/2020 | 06/05/2020 | 2020-06-08 |  |  | 110 | 2 | 0 | 115 | 30 | 146
x | Readers Branch | 2 | 40 | Belmont | 10 - Traditional | 11/17/2019 | R.Arias | 2019-11-19 | 2020-01-22 | 180 |  | 01/22/2020 | 2019-12-03 | 01/27/2020 |  |  | 2019-12-03 |  |  | 2019-12-06 | 01/27/2020 | 03/03/2020 | 2020-03-04 |  |  | 47 | 4 | 0 | 50 | 27 | 77
x | Lauradell | 1 | 65 | Helena | 30 - Craftsman | 11/18/2019 | C.Zobel | 2019-11-20 | 2020-02-04 | 120 |  | 02/04/2020 | 2019-12-04 | 02/07/2020 |  |  | 2019-12-04 |  |  | 2019-12-09 | 02/18/2020 | 03/31/2020 | 2020-04-01 |  |  | 56 | 4 | 0 | 66 | 31 | 97
x | Parkside Village | 4 | 16 | Linden III | 30 - Craftsman | 11/19/2019 | Y.Wang | 2019-11-21 | 2020-04-14 | 250 |  | 04/14/2020 | 2019-12-05 | 04/17/2020 |  |  | 2019-12-05 |  |  | 2019-12-10 | 04/27/2020 | 06/06/2020 | 2020-06-08 |  |  | 105 | 4 | 0 | 114 | 30 | 144
x | Parkside Village | 4 | 34 | Carlisle | 15 - Arts & Crafts | 11/23/2019 | C.Zobel | 2019-11-26 | 2020-04-15 | 210 |  | 04/15/2020 | 2019-12-10 | 04/22/2020 |  |  | 2019-12-10 |  |  | 2019-12-13 | 04/24/2020 | 07/06/2020 | 2020-07-07 |  |  | 102 | 6 | 0 | 109 | 52 | 161
x | Readers Branch | 2 | 4 | Linden Terrace | 30 - Craftsman | 11/25/2019 | R.Arias | 2019-11-27 | 2020-01-29 | 240 |  | 01/29/2020 | 2019-12-11 | 02/05/2020 |  |  | 2019-12-11 |  |  | 2019-12-16 | 02/05/2020 | 02/27/2020 | 2020-02-28 |  |  | 47 | 6 | 0 | 52 | 17 | 69
x | Lauradell | 1 | 58 | Raleigh | 40 - Arts & Crafts B | 11/29/2019 | C.Zobel | 2019-12-03 | 2020-03-17 | 225 |  | 03/18/2020 | 2019-12-17 | 03/24/2020 |  |  | 2019-12-17 |  |  | 2019-12-20 | 04/01/2020 | 05/08/2020 | 2020-05-11 |  |  | 77 | 5 | 0 | 88 | 28 | 116
x | Lauradell | 1 | 77 | Newport | 30 - Craftsman | 11/30/2019 | C.Zobel | 2019-12-03 | 2020-03-19 | 255 |  | 03/19/2020 | 2019-12-17 | 03/25/2020 |  |  | 2019-12-17 |  |  | 2019-12-20 | 04/01/2020 | 05/12/2020 | 2020-05-13 |  |  | 78 | 5 | 0 | 87 | 30 | 117
x | Readers Branch | 2 | 42 | Corvallis | 30 - Craftsman | 12/12/2019 | C.Zobel | 2019-12-16 | 2020-01-22 | 150 |  | 01/23/2020 | 2019-12-30 | 01/27/2020 |  |  | 2019-12-30 |  |  | 2020-01-02 | 01/30/2020 | 03/03/2020 | 2020-03-04 |  |  | 29 | 3 | 0 | 35 | 24 | 59
x | Readers Branch |  | 025 | Hartford Terrace | 30 - Craftsman | 2019-12-27 | C.Zobel | 2019-12-31 | 2019-02-12 | 480 |  | 02/18/2019 | 2020-01-14 | 2019-03-05 |  |  | 2020-01-14 |  |  | 2020-01-17 | 04/10/2019 | 2019-05-21 | 2019-05-22 |  | rear covered deck w/ framed walls on side | -230 | 12 | 0 | -189 | 30 | -159
x | Readers Branch | 2 | 37 | Belmont Terrace | 30 - Craftsman | 12/29/2019 | C.Zobel | 2019-12-31 | 2020-01-16 | 210 |  | 01/22/2020 | 2020-01-14 | 01/28/2020 |  |  | 2020-01-14 |  |  | 2020-01-17 | 01/30/2020 | 02/27/2020 | 2020-02-28 |  |  | 13 | 5 | 0 | 23 | 21 | 44
x | Parkside Village | 4 | 54 | Corvallis | 10 - Traditional | 12/31/2019 | Y.Wang | 2020-01-02 | 2020-04-17 | 300 |  | 04/17/2020 | 2020-01-16 | 04/23/2020 |  |  | 2020-01-16 |  |  | 2020-01-21 | 04/26/2020 | 06/04/2020 | 2020-06-05 |  |  | 78 | 5 | 0 | 83 | 29 | 113
x | Harpers Mill | 4 | 30 | Beverly | 10 - Traditional | 01/04/2020 | C.Zobel | 2020-01-07 | 2020-01-28 | 180 |  | 01/29/2020 | 2020-01-21 | 02/04/2020 |  |  | 2020-01-21 |  |  | 2020-01-24 | 02/05/2020 | 03/09/2020 | 2020-03-10 |  |  | 16 | 5 | 0 | 22 | 24 | 46
x | Readers Branch | 3 | 33 | Corvallis | 20 - Colonial | 01/17/2020 | Y.Wang | 2020-01-21 | 2020-03-30 | 250 |  | 03/31/2020 | 2020-02-04 |  |  |  | 2020-02-04 |  |  | 2020-02-07 |  |  | 1900-01-01 |  |  | 51 | -31372 | 0 | -31321 | 0 | -31320
x | Readers Branch | 3 | 13 | Corvallis | 30 - Craftsman | 01/19/2020 | Y.Wang | 2020-01-21 | 2020-04-01 | 300 |  | 04/02/2020 | 2020-02-04 |  |  |  | 2020-02-04 |  |  | 2020-02-07 |  |  | 1900-01-01 |  |  | 52 | -31374 | 0 | -31321 | 0 | -31320
x | Readers Branch | 3 | 31 | Corvallis | 30 - Craftsman | 01/22/2020 | Y.Wang | 2020-01-24 | 2020-04-02 | 300 |  | 04/03/2020 | 2020-02-07 | 04/08/2020 |  |  | 2020-02-07 |  |  | 2020-02-12 | 04/03/2020 | 04/17/2020 | 2020-04-20 |  |  | 51 | 4 | 0 | 52 | 11 | 63
x | Readers Branch | 3 | 15 | Fulton Terrace | A - Colonial | 01/24/2020 | C.Zobel | 2020-01-28 | 2020-04-03 | 300 |  | 04/06/2020 | 2020-02-11 | 04/20/2020 |  |  | 2020-02-11 |  |  | 2020-02-14 | 05/07/2020 | 06/29/2020 | 2020-06-30 |  |  | 50 | 11 | 0 | 74 | 38 | 112
x | Readers Branch | 3 | 26 | Linden III | 30 - Craftsman | 01/30/2020 | Y.Wang | 2020-02-03 | 2020-04-06 | 300 |  | 04/06/2020 | 2020-02-17 | 04/10/2020 |  |  | 2020-02-17 |  |  | 2020-02-20 | 05/07/2020 | 06/27/2020 | 2020-06-29 |  |  | 47 | 5 | 0 | 70 | 37 | 107
x | Readers Branch | 2 | 17 | Linden Terrace | 25 - Folk Victorian | 01/31/2020 | C.Zobel | 2020-02-04 | 2020-02-20 | 300 |  | 02/26/2020 | 2020-02-18 | 03/04/2020 |  |  | 2020-02-18 |  |  | 2020-02-21 | 03/05/2020 | 03/25/2020 | 2020-03-26 |  |  | 14 | 6 | 0 | 24 | 15 | 39
x | Readers Branch | 2 | 9 | Linden III | 10 - Traditional | 01/31/2020 | C.Zobel | 2020-02-04 | 2020-03-04 | 330 |  | 03/06/2020 | 2020-02-18 | 03/12/2020 |  |  | 2020-02-18 |  |  | 2020-02-21 | 03/12/2020 | 04/072020 | #VALUE! |  |  | 23 | 5 | 0 | 29 | #VALUE! | #VALUE!
x | Parkside Village | 4 | 45 | Linden III | 30 - Craftsman | 01/31/2020 | Y.Wang | 2020-02-04 | 2020-04-17 | 300 |  | 04/17/2020 | 2020-02-18 | 04/27/2020 |  |  | 2020-02-18 |  |  | 2020-02-21 | 05/26/2020 | 07/04/2020 | 2020-07-06 |  |  | 55 | 7 | 0 | 82 | 29 | 111
x | Lauradell | 1 | 98 | Helena | 20 - Arts & Crafts | 02/10/2020 | C.Zobel | 2020-02-12 | 2020-03-20 | 120 |  | 03/20/2020 | 2020-02-26 | 04/01/2020 |  |  | 2020-02-26 |  |  | 2020-03-02 | 04/09/2020 | 05/12/2020 | 2020-05-13 |  |  | 29 | 9 | 0 | 43 | 24 | 67
x | Readers Branch | 3 | 16 | Hartford Terrace | 10 - Traditional | 02/11/2020 | C.Zobel | 2020-02-13 | 2020-04-13 | 360 |  | 04/15/2020 | 2020-02-27 | 04/22/2020 |  |  | 2020-02-27 |  |  | 2020-03-03 | 04/24/2020 | 08/10/2020 | 2020-08-11 |  | zero entry | 44 | 6 | 0 | 53 | 77 | 130
x | Readers Branch | 2 | 18 | Belmont Terrace | 30 - Arts & Crafts | 02/14/2020 | C.Zobel | 2020-02-18 | 2020-03-11 | 195 |  | 03/12/2020 | 2020-03-03 | 03/23/2020 |  |  | 2020-03-03 |  |  | 2020-03-06 | 04/07/2020 | 04/07/2020 | 2020-04-08 |  |  | 18 | 8 | 0 | 37 | 1 | 38
x | Readers Branch | 3 | 25 | Corvallis | 40 - European | 02/14/2020 | Y.Wang | 2020-02-18 | 2020-04-03 | 300 |  | 04/04/2020 | 2020-03-03 | 04/09/2020 |  |  | 2020-03-03 |  |  | 2020-03-06 | 05/08/2020 | 06/20/2020 | 2020-06-22 |  |  | 35 | 4 | 0 | 60 | 31 | 91
x | Readers Branch | 2 | 25 | Linden III | 10 - Traditional | 02/21/2020 | C.Zobel | 2020-02-25 | 2020-03-13 | 180 |  | 03/16/2020 | 2020-03-10 | 03/18/2020 |  |  | 2020-03-10 |  |  | 2020-03-13 | 03/26/2020 | 04/21/2020 | 2020-04-22 |  |  | 15 | 3 | 0 | 24 | 19 | 43
x | Lauradell | 1 | 59 | Hartford II | B - Craftsman | 02/27/2020 | C.Zobel | 2020-03-02 | 2020-03-23 | 180 |  | 03/23/2020 | 2020-03-16 | 03/26/2020 |  |  | 2020-03-16 |  |  | 2020-03-19 | 06/01/2020 | 06/08/2020 | 2020-06-09 |  |  | 17 | 4 | 0 | 67 | 6 | 73
x | Parkside Village | 4 | 18 | Linden III | 30 - Craftsman | 02/27/2020 | C.Zobel | 2020-03-02 | 2020-04-17 | 135 |  | 04/17/2020 | 2020-03-16 | 04/23/2020 |  |  | 2020-03-16 |  |  | 2020-03-19 | 04/27/2020 | 08/05/2020 | 2020-08-06 |  |  | 36 | 5 | 0 | 42 | 73 | 115
x | Harpers Mill | 4 | 24 | Hartford Terrace | 10 - Traditional | 03/03/2020 | Y.Wang | 2020-03-05 | 2020-03-17 | 250 |  | 03/18/2020 | 2020-03-19 | 03/26/2020 |  |  | 2020-03-19 |  |  | 2020-03-24 | 03/30/2020 |  | 1900-01-01 |  |  | 10 | 7 | 0 | 19 | -31371 | -31352
x | Readers Branch | 2 | 7 | Hartford Terrace | 30 - Craftsman | 03/07/2020 | Y.Wang | 2020-03-10 | 2020-03-20 | 350 |  | 03/23/2020 | 2020-03-24 |  |  |  | 2020-03-24 |  |  | 2020-03-27 |  |  | 1900-01-01 |  |  | 9 | -31366 | 0 | -31356 | 0 | -31355
x | Harpers Mill | 2 | 36 | Beverly | 15 - Arts & Crafts | 03/7/2020 | C.Zobel | 2020-03-10 | 2020-03-31 | 90 |  | 03/31/2020 | 2020-03-24 | 04/02/2020 |  |  | 2020-03-24 |  |  | 2020-03-27 | 04/06/2020 | 06/05/2020 | 2020-06-08 |  |  | 16 | 3 | 0 | 20 | 45 | 65
x | Lauradell | 1 | 21 | Helena | 30 - Craftsman | 03/08/2020 | Y.Wang | 2020-03-10 | 2020-04-01 | 250 |  | 04/01/2020 | 2020-03-24 |  |  |  | 2020-03-24 |  |  | 2020-03-27 |  |  | 1900-01-01 |  |  | 17 | -31373 | 0 | -31356 | 0 | -31355
x | Readers Branch | 2 | 43 | Belmont | 30 - Arts & Crafts | 03/12/2020 | Y.Wang | 2020-03-16 | 2020-03-23 | 300 |  | 03/30/2020 | 2020-03-30 |  |  |  | 2020-03-30 |  |  | 2020-04-02 |  |  | 1900-01-01 |  |  | 7 | -31371 | 0 | -31360 | 0 | -31359
x | Harpers Mill | 4 | 31 | Corvallis | 20 - Colonial | 2020-03-14 | C.Zobel | 2020-03-17 | 2020-03-30 | 180 |  | 2020-03-31 | 2020-03-31 | 2020-04-03 |  |  | 2020-03-31 |  |  | 2020-04-03 | 2020-04-09 | 2020-04-27 | 2020-04-28 |  |  | 10 | 4 | 0 | 18 | 13 | 31
x | Readers Branch | 3 | 52 | Corvallis | 20 - Colonial | 03/14/2020 | Y.Wang | 2020-03-17 | 2020-04-08 | 360 |  | 04/08/2020 | 2020-03-31 | 04/11/2020 |  |  | 2020-03-31 |  |  | 2020-04-03 | 04/24/2020 | 06/10/2020 | 2020-06-11 |  |  | 17 | 3 | 0 | 29 | 34 | 63
x | Readers Branch | 2 | 5 | Linden Terrace | 25 - Folk Victorian | 03/15/2020 | C.Zobel | 2020-03-17 | 2020-04-08 | 150 |  | 04/10/2020 | 2020-03-31 | 04/20/2020 |  |  | 2020-03-31 |  |  | 2020-04-03 | 04/21/2020 | 05/21/2020 | 2020-05-22 |  |  | 17 | 7 | 0 | 26 | 23 | 49
x | Readers Branch | 3 | 24 | Linden III | 30 - Craftsman | 04/01/2020 | Y.Wang | 2020-04-03 | 2020-04-17 | 300 |  | 04/17/2020 | 2020-04-17 | 04/30/2020 |  |  | 2020-04-17 |  |  | 2020-04-22 | 04/27/2020 | 08/05/2020 | 2020-08-06 |  |  | 12 | 10 | 0 | 18 | 73 | 91
x | Readers Branch | 2 | 32 | Fulton | BSE - Arts & Crafts | 04/19/2020 | C.Zobel | 2020-04-21 | 2020-04-30 | 300 |  | 05/01/2020 | 2020-05-05 | 05/11/2020 |  |  | 2020-05-05 |  |  | 2020-05-08 | 05/12/2020 | 05/21/2020 | 2020-05-22 |  |  | 8 | 7 | 0 | 16 | 8 | 24
x | Parkside Village | 4 | 40 | Belmont | 10 - Traditional | 04/26/2020 | C.Zobel | 2020-04-28 | 2020-05-21 | 90 |  | 05/21/2020 | 2020-05-12 | 05/29/2020 |  |  | 2020-05-12 |  |  | 2020-05-15 | 06/02/2020 | 07/15/2020 | 2020-07-16 |  |  | 18 | 7 | 0 | 26 | 32 | 58
x | Cypress Creek | 7C | 349 | Hartford II | B - Craftsman | 04/29/2020 | C.Zobel | 2020-05-01 | 2020-05-13 | 240 |  | 05/13/2020 | 2020-05-15 | 06/04/2020 |  |  | 2020-05-15 |  |  | 2020-05-20 | 06/04/2020 | 07/23/2020 | 2020-07-24 |  |  | 10 | 17 | 0 | 26 | 36 | 62
x | Cypress Creek | 7B | 328 | Linden III | 30 - Craftsman | 04/29/2020 | C.Zobel | 2020-05-01 | 2020-05-19 | 540 |  | 05/20/2020 | 2020-05-15 | 06/10/2020 |  |  | 2020-05-15 |  |  | 2020-05-20 | 06/10/2020 | 07/22/2020 | 2020-07-23 |  | additional attached single garage | 14 | 16 | 0 | 30 | 31 | 61
x | Parkside Village | 4 | 19 | Corvallis | 30 - Craftsman | 04/29/2020 | Y.Wang | 2020-05-01 | 2020-05-21 | 280 |  | 05/21/2020 | 2020-05-15 | 05/28/2020 |  |  | 2020-05-15 |  |  | 2020-05-20 | 06/03/2020 | 06/05/2020 | 2020-06-08 |  |  | 16 | 6 | 0 | 25 | 3 | 28
x | Parkside Village | 4 | 39 | Linden III | 10 - Traditional | 04/29/2020 | Y.Wang | 2020-05-01 | 2020-05-26 | 280 |  | 05/26/2020 | 2020-05-15 | 06/05/2020 |  |  | 2020-05-15 |  |  | 2020-05-20 | 07/03/2020 | 07/05/2020 | 2020-07-06 |  |  | 19 | 9 | 0 | 47 | 1 | 48
x | Parkside Village | 4 | 41 | Fulton | B - Folk Victorian | 05/14/2020 | C.Zobel | 2020-05-18 | 2020-08-28 | 240 |  | 08/28/2020 | 2020-06-01 | 09/03/2020 |  |  | 2020-06-01 |  |  | 2020-06-04 | 09/08/2020 | 10/06/2020 | 2020-10-07 |  |  | 76 | 5 | 0 | 83 | 21 | 104
x | Parkside Village | 4 | 36 | Carlisle | 30 - Craftsman | 05/15/2020 | C.Zobel | 2020-05-19 | 2020-06-01 | 240 |  | 06/02/2020 | 2020-06-02 | 06/04/2020 |  |  | 2020-06-02 |  |  | 2020-06-05 | 06/09/2020 | 08/20/2020 | 2020-08-21 |  | extended family room | 11 | 3 | 0 | 17 | 53 | 70
x | Cypress Creek | 7C | 346 | Savannah | B - Craftsman | 05/16/2020 | C.Zobel | 2020-05-19 | 2020-05-27 | 360 |  | 05/29/2020 | 2020-06-02 | 06/19/2020 |  |  | 2020-06-02 |  |  | 2020-06-05 | 06/22/2020 | 07/30/2020 | 2020-07-31 |  |  | 7 | 16 | 0 | 25 | 29 | 54
x | Readers Branch | 3 | 43 | Corvallis | 40 - European | 05/20/2020 | Y.Wang | 2020-05-22 | 2020-06-08 | 300 |  | 06/08/2020 | 2020-06-05 | 06/10/2020 |  |  | 2020-06-05 |  |  | 2020-06-10 | 06/18/2020 | 08/01/2020 | 2020-08-03 |  |  | 13 | 3 | 0 | 21 | 32 | 53
x | Lauradell | 1 | 73 | Raleigh | 10 - Traditional | 05/22/2020 | C.Zobel | 2020-05-26 | 2020-06-03 | 180 |  | 06/04/2020 | 2020-06-09 | 06/10/2020 |  |  | 2020-06-09 |  |  | 2020-06-12 | 06/10/2020 | 07/16/2020 | 2020-07-17 |  |  | 8 | 5 | 0 | 13 | 27 | 40
x | Parkside Village | 4 | 44 | Linden III | 25 - Folk Victorian | 05/22/2020 | C.Zobel | 2020-05-26 | 2020-06-09 | 165 |  | 06/09/2020 | 2020-06-09 | 06/11/2020 |  |  | 2020-06-09 |  |  | 2020-06-12 | 06/17/2020 | 08/20/2020 | 2020-08-21 |  |  | 12 | 3 | 0 | 18 | 47 | 65
x | Parkside Village | 4 | 35 | Linden III | 30 - Craftsman | 05/23/2020 | C.Zobel | 2020-05-26 | 2020-06-10 | 135 |  | 06/10/2020 | 2020-06-09 | 06/16/2020 |  |  | 2020-06-09 |  |  | 2020-06-12 | 06/24/2020 | 08/20/2020 | 2020-08-21 |  |  | 12 | 5 | 0 | 22 | 42 | 64
x | Lauradell | 1 | 74 | Hadley | 10 - Traditional | 05/24/2020 | C.Zobel | 2020-05-26 | 2020-06-15 | 150 |  | 06/16/2020 | 2020-06-09 | 06/17/2020 |  |  | 2020-06-09 |  |  | 2020-06-12 | 06/25/2020 | 07/16/2020 | 2020-07-17 |  |  | 15 | 2 | 0 | 23 | 16 | 39
x | McRea & Lacy | 1 | 001 | Laurel | —— | 05/27/2020 | Y.Wang | 2020-05-29 | 2020-04-22 | 300 |  | 10/07/2019 | 2020-06-12 | 12/11/2019 |  |  | 2020-06-12 |  |  | 2020-06-17 |  |  | 1900-01-01 |  |  | -27 | 48 | 0 | -31414 | 0 | -31413
x | McRae & Lacy | 1 | 005 | Laurel | —— | 05/27/2020 | Y.Wang | 2020-05-29 | 2020-04-22 | 300 |  | 10/07/2019 | 2020-06-12 | 12/11/2019 |  |  | 2020-06-12 |  |  | 2020-06-17 |  |  | 1900-01-01 |  |  | -27 | 48 | 0 | -31414 | 0 | -31413
x | Harpers Mill | 4 | 3 | Beverly | 30 - Craftsman | 05/29/2020 | C.Zobel | 2020-06-02 | 2020-06-11 | 120 |  | 06/11/2020 | 2020-06-16 | 06/15/2020 |  |  | 2020-06-16 |  |  | 2020-06-19 | 06/22/2020 | 07/15/2020 | 2020-07-16 |  |  | 9 | 3 | 0 | 16 | 18 | 34
x | Readers Branch | 4 | 45 | Linden III | 30 - Craftsman | 05/31/2020 | Y.Wang | 2020-06-02 | 2020-06-15 | 300 |  | 06/15/2020 | 2020-06-16 | 06/17/2020 |  |  | 2020-06-16 |  |  | 2020-06-19 | 06/26/2020 | 08/04/2020 | 2020-08-05 |  |  | 10 | 3 | 0 | 19 | 28 | 47
x | Parkside Village | 4 | 33 | Belmont | 20 - Craftsman | 05/31/2020 | Y.Wang | 2020-06-02 | 2020-08-31 | 280 |  | 09/26/2020 | 2020-06-16 |  |  |  | 2020-06-16 |  |  | 2020-06-19 |  |  | #VALUE! |  |  | 65 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE!
x | Ford's Colony | S3 | 272 | Corvallis | 40 - European | 06/02/2020 | C.Zobel | 2020-06-04 | 2020-06-18 | 270 |  | 06/18/2020 | 2020-06-18 | 06/24/2020 |  |  | 2020-06-18 |  |  | 2020-06-23 | 06/30/2020 | 12/29/2020 | 2020-12-30 |  |  | 12 | 5 | 0 | 20 | 131 | 151
x | Harpers Mill | 4 | 11 | Beverly | 30 - Craftsman | 06/03/2020 | Y.Wang | 2020-06-05 | 2020-06-18 | 280 |  | 06/26/2020 | 2020-06-19 | 07/02/2020 |  |  | 2020-06-19 |  |  | 2020-06-24 | 07/01/2020 | 08/20/2020 | 2020-08-21 |  |  | 11 | 5 | 0 | 20 | 37 | 57
x | Cypress Creek | 7C | 358 | Linden III | 30 - Craftsman | 06/07/2020 | C.Zobel | 2020-06-09 | 2020-06-26 | 210 |  | 06/26/2020 | 2020-06-23 | 07/10/2020 |  |  | 2020-06-23 |  |  | 2020-06-26 | 07/20/2020 | 08/14/2020 | 2020-08-17 |  |  | 14 | 11 | 0 | 30 | 20 | 50
x | Harpers Mill | 4 | 2 | Beverly | 10 - Traditional | 06/07/2020 | C.Zobel | 2020-06-09 | 2020-06-30 | 75 |  | 06/30/2020 | 2020-06-23 | 07/01/2020 |  |  | 2020-06-23 |  |  | 2020-06-26 | 07/01/2020 | 08/20/2020 | 2020-08-21 |  |  | 16 | 2 | 0 | 17 | 37 | 54
x | Harpers Mill | 4 | 18 | Hadley | 10 - Traditional | 06/12/2020 | C.Zobel | 2020-06-16 | 2020-07-01 | 90 |  | 07/01/2020 | 2020-06-30 | 07/08/2020 |  |  | 2020-06-30 |  |  | 2020-07-03 | 07/10/2020 | 07/30/2020 | 2020-07-31 |  |  | 13 | 6 | 0 | 20 | 15 | 35
x | Harpers Mill | 4 | 14 | Corvallis | 40 - European | 06/14/2020 | Y.Wang | 2020-06-16 | 2020-06-30 | 280 |  | 06/30/2020 | 2020-06-30 | 07/08/2020 |  |  | 2020-06-30 |  |  | 2020-07-03 | 07/01/2020 | 07/08/2020 | 2020-07-09 |  |  | 11 | 7 | 0 | 12 | 6 | 18
x | McRae & Lacy | 1 | 002 | Laurel | —— | 06/19/2020 | Y.Wang | 2020-06-23 | 2020-04-22 | 300 |  | 10/07/2019 | 2020-07-07 | 12/11/2019 |  |  | 2020-07-07 |  |  | 2020-07-10 |  |  | 1900-01-01 |  |  | -44 | 48 | 0 | -31431 | 0 | -31430
x | Parkside Village | 4 | 22 | Fulton | BSE - Arts & Crafts | 06/20/2020 | C.Zobel | 2020-06-23 | 2020-08-25 | 150 |  | 08/25/2020 | 2020-07-07 | 08/28/2020 |  |  | 2020-07-07 |  |  | 2020-07-10 | 09/08/2020 | 10/23/2020 | 2020-10-26 |  |  | 46 | 4 | 0 | 56 | 34 | 90
x | Harpers Mill | 4 | 19 | Hartford II | BSE - Arts & Crafts | 06/22/2020 | Y.Wang | 2020-06-24 | 2020-08-06 | 280 |  | 08/06/2020 | 2020-07-08 | 08/13/2020 |  |  | 2020-07-08 |  |  | 2020-07-13 | 08/15/2020 | 08/18/2020 | 2020-08-19 |  |  | 33 | 6 | 0 | 39 | 2 | 42
x | The Parke @ Cypress Creek | 1 | 81 | Easton | 10 - Traditional | 06/22/2020 | C.Zobel | 2020-06-24 | 2020-10-30 | 240 |  | 11/02/2020 | 2020-07-08 | 11/13/2020 |  |  | 2020-07-08 |  |  | 2020-07-13 | 02/08/2021 | 04/02/2021 | 2021-04-05 |  |  | 94 | 10 | 0 | 165 | 40 | 205
x | Readers Branch | 3 | 41 | Belmont | 20 - Craftsman | 06/22/2020 | Y.Wang | 2020-06-24 | 2020-07-15 | 300 |  | 07/15/2020 | 2020-07-08 | 07/17/2020 |  |  | 2020-07-08 |  |  | 2020-07-13 | 07/18/2020 | 08/11/2020 | 2020-08-12 |  |  | 17 | 3 | 0 | 19 | 17 | 37
x | Lauradell | 1 | 49 | Corvallis | 40 - European | 06/27/2020 | C.Zobel | 2020-06-30 | 10/08/2020 | 720 |  | 10/12/2020 | 2020-07-14 | 10/15/2020 |  |  | 2020-07-14 |  |  | 2020-07-17 | 10/28/2020 | 11/16/2020 | 2020-11-17 |  | zero entry garage / slab on grade | 73 | 4 | 0 | 87 | 14 | 101
x | Lauradell | 1 | 64 | Raleigh | 20 - Arts & Crafts A | 06/30/2020 | C.Zobel | 2020-07-02 | 2020-07-15 | 210 |  | 07/16/2020 | 2020-07-16 | 07/21/2020 |  |  | 2020-07-16 |  |  | 2020-07-21 | 07/21/2020 | 08/12/2020 | 2020-08-13 |  |  | 11 | 4 | 0 | 15 | 17 | 32
x | The Parke @ Cypress Creek | 1 | 78 | Easton | 10 - Traditional | 06/30/2020 | C.Zobel | 2020-07-02 | 2020-09-11 | 240 |  | 09/22/2020 | 2020-07-16 | 10/20/2020 |  |  | 2020-07-16 |  |  | 2020-07-21 | 10/30/2020 | 03/29/2021 | 2021-03-30 |  |  | 53 | 21 | 0 | 88 | 107 | 195
x | Parkside Village | 4 | 28 | Linden III | 30 - Craftsman | 07/09/2020 | C.Zobel | 2020-07-13 | 2020-09-09 | 225 |  | 09/09/2020 | 2020-07-27 | 09/14/2020 |  |  | 2020-07-27 |  |  | 2020-07-30 | 09/29/2020 | 11/02/2020 | 2020-11-03 |  |  | 44 | 4 | 0 | 58 | 25 | 83
x | Cypress Creek | 7C | 338 | Westminster | B - Craftsman | 07/13/2020 | Y.Wang | 2020-07-15 | 2020-08-07 | 210 |  | 08/06/2020 | 2020-07-29 | 08/26/2020 |  |  | 2020-07-29 |  |  | 2020-08-03 | 08/20/2020 | 09/25/2020 | 2020-09-28 |  |  | 19 | 15 | 0 | 28 | 27 | 55
x | Harpers Mill | 4 | 23 | Linden Terrace | 25 - Folk Victorian | 07/16/2020 | C.Zobel | 2020-07-20 | 2020-08-10 | 270 |  | 08/11/2020 | 2020-08-03 | 08/21/2020 |  |  | 2020-08-03 |  |  | 2020-08-06 | 08/24/2020 | 09/16/2020 | 2020-09-17 |  |  | 17 | 9 | 0 | 27 | 18 | 45
x | Lauradell | 1 | 60 | Raleigh | 40 - Arts & Crafts B | 07/19/2020 | Y.Wang | 2020-07-21 | 2020-08-04 | 300 |  | 08/04/2020 | 2020-08-04 | 08/07/2020 |  |  | 2020-08-04 |  |  | 2020-08-07 | 08/15/2020 | 08/10/2020 | 2020-08-11 |  |  | 11 | 4 | 0 | 19 | -5 | 16
x | Harpers Mill | 4 | 36 | Carlisle | 30 - Craftsman | 07/20/2020 | C.Zobel | 2020-07-22 | 2020-09-03 | 255 |  | 09/04/2020 | 2020-08-05 | 09/10/2020 |  |  | 2020-08-05 |  |  | 2020-08-10 | 09/14/2020 | 09/30/2020 | 2020-10-01 |  |  | 33 | 5 | 0 | 40 | 13 | 53
x | Lauradell | 1 | 94 | Newport | 40 - New England | 07/25/2020 | C.Zobel | 2020-07-28 | 2020-08-13 | 135 |  | 08/13/2020 | 2020-08-11 | 08/19/2020 |  |  | 2020-08-11 |  |  | 2020-08-14 | 08/24/2020 | 09/10/2020 | 2020-09-11 |  |  | 13 | 5 | 0 | 20 | 14 | 34
x | Cypress Creek | 7C | 348 | Carlisle | 15 - Arts & Crafts | 07/26/2020 | Y.Wang | 2020-07-28 | 2020-09-08 | 250 |  | 09/08/2020 | 2020-08-11 |  |  |  | 2020-08-11 |  |  | 2020-08-14 |  |  | #VALUE! |  |  | 31 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE!
x | Harpers Mill | 4 | 4 | Hartford II | BSE - Arts & Crafts | 07/30/2020 | C.Zobel | 2020-08-03 | 11/06/2020 | 240 |  | 11/09/2020 | 2020-08-17 | 11/23/2020 |  |  | 2020-08-17 |  |  | 2020-08-20 | 12/03/2020 | 12/18/2020 | 2020-12-21 |  |  | 71 | 11 | 0 | 90 | 12 | 102
x | Lauradell | 1 | 68 | Manchester | 20 - Arts & Crafts | 07/31/2020 | C.Zobel | 2020-08-04 | 2020-08-14 | 165 |  | 08/21/2020 | 2020-08-18 | 08/26/2020 |  |  | 2020-08-18 |  |  | 2020-08-21 | 09/28/2020 | 10/26/2020 | 2020-10-27 |  |  | 10 | 4 | 0 | 41 | 21 | 62
x | Cypress Creek | 7C | 345 | Carlisle | 15 - Arts & Crafts | 07/31/2020 | Y.Wang | 2020-08-04 | 2020-08-18 | 280 |  | 08/18/2020 | 2020-08-18 | 09/02/2020 |  |  | 2020-08-18 |  |  | 2020-08-21 | 09/02/2020 | 09/22/2020 | 2020-09-23 |  |  | 12 | 12 | 0 | 23 | 15 | 38
x | Givens Farm | 12 | 92 | Savannah | BSE - Arts & Crafts | 08/09/2020 | C.Zobel | 2020-08-11 | 2020-08-21 | 120 |  | 08/21/2020 | 2020-08-25 | 09/15/2020 |  |  | 2020-08-25 |  |  | 2020-08-28 | 09/15/2020 | 01/18/2021 | 2021-01-19 |  |  | 9 | 18 | 0 | 26 | 90 | 116
x | Givens Farm | 12 | 93 | Savannah | A - Folk Victorian | 08/09/2020 | C.Zobel | 2020-08-11 | 2020-08-26 | 120 |  | 08/26/2020 | 2020-08-25 | 09/11/2020 |  |  | 2020-08-25 |  |  | 2020-08-28 | 09/15/2020 | 01/07/2021 | 2021-01-08 |  |  | 12 | 13 | 0 | 26 | 83 | 109
x | Givens Farm | 12 | 96 | Linden III | 10 - Traditional | 08/10/2020 | C.Zobel | 2020-08-12 | 2020-09-17 | 360 |  | 09/22/2020 | 2020-08-26 | 09/29/2020 |  |  | 2020-08-26 |  |  | 2020-08-31 | 11/04/2020 | 12/30/2020 | 2020-12-31 |  | basement (old style) | 28 | 6 | 0 | 62 | 41 | 103
x | Readers Branch | 3 | 5 | Corvallis | 30 - Craftsman | 08/20/2020 | C.Zobel | 2020-08-24 | 11/03/2020 | 120 |  | 11/05/2020 | 2020-09-07 | 11/09/2020 |  |  | 2020-09-07 |  |  | 2020-09-10 | 11/16/2020 | 12/10/2020 | 2020-12-11 |  |  | 53 | 3 | 0 | 62 | 19 | 81
x | Readers Branch | 3 | 45 | Hartford II | B - Craftsman | 08/21/2020 | C.Zobel | 2020-08-25 | 2020-09-01 | 300 |  | 09/01/2020 | 2020-09-08 | 09/04/2020 |  |  | 2020-09-08 |  |  | 2020-09-11 | 09/28/2020 | 10/19/2020 | 2020-10-20 |  |  | 7 | 4 | 0 | 26 | 16 | 42
x | Lankford Crossing | 2 | 20 | Hartford II | BSE - Arts & Crafts | 08/26/2020 | C.Zobel | 2020-08-28 | 10/29/2020 | 300 |  | 10/30/2020 | 2020-09-11 | 11/03/2020 |  |  | 2020-09-11 |  |  | 2020-09-16 | 11/04/2020 | 12/01/2020 | 2020-12-02 |  |  | 46 | 3 | 0 | 50 | 20 | 70
x | Harpers Mill | 4 | 21 | Linden Terrace | 25 - Folk Victorian | 08/27/2020 | C.Zobel | 2020-08-31 | 11/02/2020 | 240 |  | 11/06/2020 | 2020-09-14 | 11/11/2020 |  |  | 2020-09-14 |  |  | 2020-09-17 | 11/17/2020 | 12/11/2020 | 2020-12-14 |  |  | 47 | 4 | 0 | 58 | 19 | 77
x | Lauradell | 1 | 48 | Helena | 20 - Arts & Crafts | 08/28/2020 | C.Zobel | 2020-09-01 | 10/01/2020 | 240 |  | 10/05/2020 | 2020-09-15 | 10/12/2020 |  |  | 2020-09-15 |  |  | 2020-09-18 | 10/15/2020 | 11/24/2020 | 2020-11-25 |  |  | 24 | 6 | 0 | 34 | 29 | 63
x | Parkside Village | 4 | 4 | Belmont | 10 - Traditional | 08/28/2020 | C.Zobel | 2020-09-01 | 11/01/2020 | 60 |  | 11/02/2020 | 2020-09-15 | 11/09/2020 |  |  | 2020-09-15 |  |  | 2020-09-18 | 11/16/2020 | 12/10/2020 | 2020-12-11 |  |  | 45 | 6 | 0 | 56 | 19 | 75
x | Parkside Village | 4 | 59 | Carlisle | 10 - Traditional | 08/28/2020 | C.Zobel | 2020-09-01 | 11/05/2020 | 240 |  | 11/06/2020 | 2020-09-15 | 11/13/2020 |  |  | 2020-09-15 |  |  | 2020-09-18 | 11/18/2020 | 12/18/2020 | 2020-12-21 |  |  | 49 | 6 | 0 | 58 | 23 | 81
x | Harpers Mill | 4 | 13 | Beverly | 10 - Traditional | 08/29/2020 | C.Zobel | 2020-09-01 | 11/03/2020 | 240 |  | 11/05/2020 | 2020-09-15 | 11/09/2020 |  |  | 2020-09-15 |  |  | 2020-09-18 | 11/20/2020 | 12/28/2020 | 2020-12-29 |  |  | 46 | 3 | 0 | 59 | 27 | 86
x | McRae & Lacy | 1 | 006 | Laurel | —— | 08/30/2020 | Y.Wang | 2020-09-01 | 2020-04-22 | 300 |  | 10/07/2019 | 2020-09-15 | 12/11/2019 |  |  | 2020-09-15 |  |  | 2020-09-18 |  |  | 1900-01-01 |  |  | -94 | 48 | 0 | -31481 | 0 | -31480
x | Lauradell | 1 | 57 | Savannah | B - Craftsman | 08/31/2020 | C.Zobel | 2020-09-02 | 10/05/2020 | 240 |  | 10/06/2020 | 2020-09-16 | 10/13/2020 |  |  | 2020-09-16 |  |  | 2020-09-21 | 10/15/2020 | 11/03/2020 | 2020-11-04 |  |  | 25 | 6 | 0 | 33 | 14 | 47
x | Readers Branch | 3 | 39 | Fulton | BSE - Arts & Crafts | 08/31/2020 | C.Zobel | 2020-09-02 | 10/14/2020 | 240 |  | 10/15/2020 | 2020-09-16 | 10/21/2020 |  |  | 2020-09-16 |  |  | 2020-09-21 | 10/28/2020 | 11/09/2020 | 2020-11-10 |  |  | 32 | 5 | 0 | 42 | 9 | 51
x | Readers Branch | 3 | 63 | Fulton | BSE - Arts & Crafts | 09/04/2020 | C.Zobel | 2020-09-08 | 10/19/2020 | 270 |  | 10/22/2020 | 2020-09-22 | 11/02/2020 |  |  | 2020-09-22 |  |  | 2020-09-25 | 11/04/2020 | 11/24/2020 | 2020-11-25 |  |  | 31 | 8 | 0 | 43 | 15 | 58
x | Readers Branch | 3 | 18 | Hartford Terrace | 30 - Craftsman | 09/13/2020 | C.Zobel | 2020-09-15 | 10/31/2020 | 300 |  | 11/02/2020 | 2020-09-29 | 11/10/2020 |  |  | 2020-09-29 |  |  | 2020-10-02 | 11/12/2020 | 12/04/2020 | 2020-12-07 |  |  | 34 | 7 | 0 | 43 | 17 | 60
x | Lauradell | 1 | 41 | Hadley | 25 - Folk Victorian | 09/25/2020 | C.Zobel | 2020-09-29 | 11/01/2020 | 300 |  | 11/02/2020 | 2020-10-13 | 11/09/2020 |  |  | 2020-10-13 |  |  | 2020-10-16 | 12/29/2020 | 01/27/2021 | 2021-01-28 |  | backup generator | 25 | 6 | 0 | 67 | 22 | 89
x | Cypress Creek | 7B | 327 | Fulton | BSE - Arts & Crafts | 09/27/2020 | C.Zobel | 2020-09-29 | 10/20/2020 | 480 |  | 10/22/2020 | 2020-10-13 | 12/18/2020 |  |  | 2020-10-13 |  |  | 2020-10-16 | 12/21/2020 | 01/29/2021 | 2021-02-01 |  |  | 16 | 42 | 0 | 60 | 30 | 90
x | Givens Farm | 12 | 90 | Savannah | B - Craftsman | 09/27/2020 | C.Zobel | 2020-09-29 | 10/23/2020 | 240 |  | 10/26/2020 | 2020-10-13 | 11/04/2020 |  |  | 2020-10-13 |  |  | 2020-10-16 | 11/04/2020 | 01/18/2021 | 2021-01-19 |  |  | 19 | 8 | 0 | 27 | 54 | 81
x | Givens Farm | 12 | 91 | Savannah | A - Folk Victorian | 09/27/2020 | C.Zobel | 2020-09-29 | 10/26/2020 | 180 |  | 10/27/2020 | 2020-10-13 | 11/05/2020 |  |  | 2020-10-13 |  |  | 2020-10-16 | 11/06/2020 | 02/02/2021 | 2021-02-03 |  |  | 20 | 8 | 0 | 29 | 63 | 92
x | Harpers Mill | 4 | 38 | Hadley | 10 - Traditional | 09/29/2020 | C.Zobel | 2020-10-01 | 11/11/2020 | 240 |  | 11/11/2020 | 2020-10-15 | 11/17/2020 |  |  | 2020-10-15 |  |  | 2020-10-20 | 11/20/2020 | 12/18/2020 | 2020-12-21 |  |  | 31 | 5 | 0 | 38 | 21 | 59
x | Readers Branch | 2 | 39 | Corvallis | 30 - Craftsman | 10/04/2020 | C.Zobel | 2020-10-06 | 11/04/2020 | 180 |  | 11/05/2020 | 2020-10-20 | 11/10/2020 |  |  | 2020-10-20 |  |  | 2020-10-23 | 11/16/2020 | 12/10/2020 | 2020-12-11 |  | 2fl | 22 | 4 | 0 | 30 | 19 | 49
x | Parkside Village | 4 | 43 | Fulton | BSE - Arts & Crafts | 10/04/2020 | C.Zobel | 2020-10-06 | 11/15/2020 | 240 |  | 11/16/2020 | 2020-10-20 | 11/18/2020 |  |  | 2020-10-20 |  |  | 2020-10-23 | 11/19/2020 | 12/29/2020 | 2020-12-30 |  |  | 29 | 3 | 0 | 33 | 29 | 62
x | Readers Branch | 3 | 36 | Corvallis | 40 - European | 10/10/2020 | C.Zobel | 2020-10-13 | 11/06/2020 | 240 |  | 11/06/2020 | 2020-10-27 | 11/13/2020 |  |  | 2020-10-27 |  |  | 2020-10-30 | 11/18/2020 | 12/16/2020 | 2020-12-17 |  | backup generator, 2fl | 19 | 6 | 0 | 27 | 21 | 48
x | Givens Farm | 12 | 86 | Savannah | A - Folk Victorian | 10/11/2020 | C.Zobel | 2020-10-13 | 10/31/2020 | 120 |  | 11/02/2020 | 2020-10-27 | 11/10/2020 |  |  | 2020-10-27 |  |  | 2020-10-30 | 12/17/2020 | 02/24/2021 | 2021-02-25 |  |  | 14 | 7 | 0 | 48 | 50 | 98
x | Readers Branch | 3 | 22 | Fulton Terrace | BSE - Arts & Crafts | 10/14/2020 | C.Zobel | 2020-10-16 | 11/08/2020 | 300 |  | 11/09/2020 | 2020-10-30 | 11/18/2020 |  |  | 2020-10-30 |  |  | 2020-11-04 | 12/03/2020 | 12/16/2020 | 2020-12-17 |  |  | 17 | 8 | 0 | 36 | 10 | 46
x | Readers Branch | 3 | 46 | Corvallis | 40 - European | 10/16/2020 | C.Zobel | 2020-10-20 | 11/19/2020 | 240 |  | 11/20/2020 | 2020-11-03 | 11/30/2020 |  |  | 2020-11-03 |  |  | 2020-11-06 | 12/10/2020 | 01/21/2021 | 2021-01-22 |  | double sided fireplace / nana wall | 24 | 7 | 0 | 39 | 31 | 70
x | Harpers Mill | 4 | 42 | Belmont | 10 - Traditional | 10/22/2020 | C.Zobel | 2020-10-26 | 11/15/2020 | 120 |  | 11/16/2020 | 2020-11-09 | 11/19/2020 |  |  | 2020-11-09 |  |  | 2020-11-12 | 12/03/2020 | 12/18/2020 | 2020-12-21 |  |  | 16 | 4 | 0 | 30 | 12 | 42
x | Cypress Creek | 7C | 341 | Savannah | B - Craftsman | 10/25/2020 | C.Zobel | 2020-10-27 | 12/21/2020 | 300 |  | 12/22/2020 | 2020-11-10 | 01/07/2021 |  |  | 2020-11-10 |  |  | 2020-11-13 | 01/08/2021 | 03/15/2021 | 2021-03-16 |  | attic | 40 | 13 | 0 | 54 | 47 | 101
x | Lauradell | 1 | 28 | Helena | 30 - Craftsman | 10/26/2020 | C.Zobel | 2020-10-28 | 12/04/2020 | 360 |  | 12/07/2020 | 2020-11-11 | 12/10/2020 |  |  | 2020-11-11 |  |  | 2020-11-16 | 12/15/2020 | 01/06/2021 | 2021-01-07 |  |  | 29 | 4 | 0 | 36 | 17 | 53
x | Givens Farm | 12 | 113 | Savannah | B - Craftsman | 10/30/2020 | C.Zobel | 2020-11-03 | 12/16/2020 | 240 |  | 12/17/2020 | 2020-11-17 | 01/05/2021 |  |  | 2020-11-17 |  |  | 2020-11-20 | 01/11/2021 | 05/14/2021 | 2021-05-17 |  |  | 33 | 14 | 0 | 51 | 90 | 141
x | Parkside Village | 4 | 48 | Carlisle | 15 - Arts & Crafts | 10/31/2020 | C.Zobel | 2020-11-03 | 12/07/2020 | 360 |  | 12/10/2020 | 2020-11-17 | 12/14/2020 |  |  | 2020-11-17 |  |  | 2020-11-20 | 12/17/2020 | 01/21/2021 | 2021-01-22 |  |  | 25 | 3 | 0 | 33 | 26 | 59
x | Cypress Creek | 7C | 351 | Savannah | BSE - Arts & Crafts | 11/02/2020 | C.Zobel | 2020-11-04 | 12/22/2020 | 480 |  | 12/28/2020 | 2020-11-18 | 01/07/2021 |  |  | 2020-11-18 |  |  | 2020-11-23 | 01/08/2021 | 03/04/2021 | 2021-03-05 |  | ult. Mbath / alt. 2nd floor / 2' ext | 36 | 9 | 0 | 49 | 40 | 89
x | Parkside Village | 4 | 62 | Carlisle | 15 - Arts & Crafts | 11/05/2020 | C.Zobel | 2020-11-09 | 12/11/2020 | 120 |  | 12/11/2020 | 2020-11-23 | 12/14/2020 |  |  | 2020-11-23 |  |  | 2020-11-26 | 12/17/2020 | 01/26/2021 | 2021-01-27 |  |  | 26 | 2 | 0 | 30 | 29 | 59
x | Readers Branch | 3 | 21 | Fulton Terrace | B - Folk Victorian | 11/16/2020 | C.Zobel | 2020-11-18 | 01/04/2021 | 480 |  | 01/04/2021 | 2020-12-02 | 01/13/2021 |  |  | 2020-12-02 |  |  | 2020-12-07 | 01/13/2021 | 02/04/2021 | 2021-02-05 |  | w/ custom elevation & Florida room | 35 | 8 | 0 | 42 | 17 | 59
x | Readers Branch | 3 | 29 | Linden III | 10 - Traditional | 11/16/2020 | C.Zobel | 2020-11-18 | 01/07/2021 | 240 |  | 01/07/2021 | 2020-12-02 | 01/13/2021 |  |  | 2020-12-02 |  |  | 2020-12-07 | 01/14/2021 | 02/04/2021 | 2021-02-05 |  |  | 38 | 5 | 0 | 43 | 16 | 59
x | Givens Farm | 12 | 131 | Savannah | A - Folk Victorian | 11/23/2020 | C.Zobel | 2020-11-25 | 02/23/2021 | 360 |  | 02/24/2021 | 2020-12-09 | 03/03/2021 |  |  | 2020-12-09 |  |  | 2020-12-14 | 04/14/2021 | 05/14/2021 | 2021-05-17 |  | extend floor system under utility room | 66 | 6 | 0 | 102 | 23 | 125
x | The Parke @ Cypress Creek | 1 | 79 | Stamford | 35 - Cottage | 12/06/2020 | C.Zobel | 2020-12-08 | 01/29/2021 | 180 |  | 01/29/2021 | 2020-12-22 | 02/22/2021 |  |  | 2020-12-22 |  |  | 2020-12-25 | 03/24/2021 | 04/27/2021 | 2021-04-28 |  |  | 39 | 17 | 0 | 77 | 25 | 102
x | Harpers Mill | 4 | 5 | Hartford II | B - Craftsman | 12/06/2020 | C.Zobel | 2020-12-08 | 02/19/2021 | 300 |  | 02/22/2021 | 2020-12-22 | 02/24/2021 |  |  | 2020-12-22 |  |  | 2020-12-25 | 03/03/2021 | 04/01/2021 | 2021-04-02 |  |  | 54 | 3 | 0 | 62 | 22 | 84
x | The Parke @ Cypress Creek | 1 | 68 | Easton | 20 - Craftsman | 12/13/2020 | C.Zobel | 2020-12-15 | 02/03/2021 | 240 |  | 02/04/2021 | 2020-12-29 | 02/27/2021 |  |  | 2020-12-29 |  |  | 2021-01-01 | 03/10/2021 | 04/15/2021 | 2021-04-16 |  |  | 37 | 17 | 0 | 62 | 27 | 89
x | Givens Farm | 12 | 132 | Carlisle | 15 - Arts & Crafts | 12/17/2020 | C.Zobel | 2020-12-21 | 02/24/2021 | 360 |  | 02/25/2021 | 2021-01-04 | 03/05/2021 |  |  | 2021-01-04 |  |  | 2021-01-07 | 04/15/2021 | 05/14/2021 | 2021-05-17 |  | courtyard walls | 49 | 7 | 0 | 85 | 22 | 107
x | Cypress Creek | 00 | 233 | Linden III | 25 - Folk Victorian | 12/23/2020 | C.Zobel | 2020-12-25 | 02/02/2021 | 300 |  | 02/03/2021 | 2021-01-08 | 02/22/2021 |  |  | 2021-01-08 |  |  | 2021-01-13 | 02/25/2021 | 04/26/2021 | 2021-04-27 |  |  | 29 | 14 | 0 | 46 | 43 | 89
x | Readers Branch | 2 | 6 | Linden Terrace | 30 - Craftsman | 12/27/2020 | C.Zobel | 2020-12-29 | 01/17/2021 | 240 |  | 01/18/2021 | 2021-01-12 | 01/25/2021 |  |  | 2021-01-12 |  |  | 2021-01-15 | 01/25/2021 | 03/05/2021 | 2021-03-08 |  |  | 14 | 6 | 0 | 20 | 30 | 50
x | Lauradell | 1 | 25 | Raleigh | 40 - Arts & Crafts B | 12/28/2020 | C.Zobel | 2020-12-30 | 01/20/2021 | 240 |  | 01/21/2021 | 2021-01-13 | 02/04/2021 |  |  | 2021-01-13 |  |  | 2021-01-18 | 02/08/2021 | 03/11/2021 | 2021-03-12 |  |  | 17 | 11 | 0 | 30 | 24 | 54
x | Lauradell | 1 | 50 | Helena | 30 - Craftsman | 01/03/2021 | C.Zobel | 2021-01-05 | 01/18/2021 | 180 |  | 01/19/2021 | 2021-01-19 | 01/21/2021 |  |  | 2021-01-19 |  |  | 2021-01-22 | 01/25/2021 | 03/03/2021 | 2021-03-04 |  |  | 10 | 3 | 0 | 15 | 28 | 43
x | The Parke @ Cypress Creek | 1 | 66 | Stamford | 40 - Folk Victorian | 01/08/2021 | C.Zobel | 2021-01-12 | 02/12/2021 | 240 |  | 02/12/2021 | 2021-01-26 | 03/08/2021 |  |  | 2021-01-26 |  |  | 2021-01-29 | 03/15/2021 | 04/16/2021 | 2021-04-19 |  | backup generator | 25 | 17 | 0 | 46 | 25 | 71
x | The Parke @ Cypress Creek | 1 | 149 | Easton | 20 - Craftsman | 01/22/2021 | C.Zobel | 2021-01-26 | 03/02/2021 | 300 |  | 03/03/2021 | 2021-02-09 | 03/24/2021 |  |  | 2021-02-09 |  |  | 2021-02-12 | 04/14/2021 | 05/11/2021 | 2021-05-12 |  | backup generator | 27 | 16 | 0 | 58 | 20 | 78
x | The Parke @ Cypress Creek | 1 | 69 | Easton | 40 - Folk Victorian | 01/28/2021 | C.Zobel | 2021-02-01 | 03/03/2021 | 300 |  | 03/04/2021 | 2021-02-15 | 04/27/2021 |  |  | 2021-02-15 |  |  | 2021-02-18 | 04/28/2021 | 05/25/2021 | 2021-05-26 |  | extend family room; florida room | 24 | 39 | 0 | 64 | 20 | 84
x | Readers Branch | 3 | 2 | Fulton | B - Folk Victorian | 01/30/2021 | C.Zobel | 2021-02-02 | 03/11/2021 | 300 |  | 03/12/2021 | 2021-02-16 | 03/23/2021 |  |  | 2021-02-16 |  |  | 2021-02-19 | 03/23/2021 | 04/15/2021 | 2021-04-16 |  |  | 28 | 8 | 0 | 36 | 18 | 54
x | Lankford Crossing | 2 | 5 | Corvallis | 40 - European | 02/03/2021 | C.Zobel | 2021-02-05 | 03/08/2021 | 240 |  | 03/09/2021 | 2021-02-19 | 03/11/2021 |  |  | 2021-02-19 |  |  | 2021-02-24 | 03/30/2021 | 04/29/2021 | 2021-04-30 |  |  | 23 | 3 | 0 | 39 | 23 | 62
x | Parkside Village | 4 | 3 | Corvallis | 10 - Traditional | 02/04/2021 | C.Zobel | 2021-02-08 | 03/15/2021 | 150 |  | 03/15/2021 | 2021-02-22 | 03/23/2021 |  |  | 2021-02-22 |  |  | 2021-02-25 | 03/29/2021 | 04/22/2021 | 2021-04-23 |  |  | 27 | 7 | 0 | 37 | 19 | 56
x | Givens Farm | 12 | 97 | Linden III | 25 - Folk Victorian | 02/05/2021 | C.Zobel | 2021-02-09 | 03/25/2021 | 480 |  | 03/29/2021 | 2021-02-23 | 04/12/2021 |  |  | 2021-02-23 |  |  | 2021-02-26 | 04/22/2021 | 07/07/2021 | 2021-07-08 |  | terrace basement; covered deck | 34 | 11 | 0 | 54 | 55 | 109
x | Lauradell | 1 | 63 | Savannah | A - Folk Victorian | 02/23/2021 | C.Zobel | 2021-02-25 | 03/31/2021 | 240 |  | 04/01/2021 | 2021-03-11 | 04/07/2021 |  |  | 2021-03-11 |  |  | 2021-03-16 | 04/14/2021 | 05/07/2021 | 2021-05-10 |  |  | 26 | 5 | 0 | 36 | 18 | 54
x | Readers Branch | 3 | 38 | Hartford II | B - Craftsman | 02/28/2021 | C.Zobel | 2021-03-02 | 04/05/2021 | 300 |  | 04/06/2021 | 2021-03-16 | 04/12/2021 |  |  | 2021-03-16 |  |  | 2021-03-19 | 04/19/2021 | 05/13/2021 | 2021-05-14 |  | breakfast nook extension | 25 | 5 | 0 | 35 | 19 | 54
x | Cypress Creek | 7C | 361 | Hartford II | BSE - Arts & Crafts | 02/28/2021 | C.Zobel | 2021-03-02 | 03/16/2021 | 300 |  | 03/17/2021 | 2021-03-16 | 05/10/2021 |  |  | 2021-03-16 |  |  | 2021-03-19 | 05/13/2021 | 06/16/2021 | 2021-06-17 |  | extend raised patio | 11 | 39 | 0 | 53 | 25 | 78
x | Lankford Crossing | 2 | 16 | Savannah | B - Craftsman | 03/04/2021 | C.Zobel | 2021-03-08 | 04/01/2021 | 240 |  | 04/02/2021 | 2021-03-22 | 04/08/2021 |  |  | 2021-03-22 |  |  | 2021-03-25 | 04/21/2021 | 05/27/2021 | 2021-05-28 |  | attic | 20 | 5 | 0 | 34 | 27 | 61
x | Cypress Creek | 7C | 343 | Linden III | 10 - Traditional | 03/08/2021 | C.Zobel | 2021-03-10 | 04/02/2021 | 300 |  | 04/06/2021 | 2021-03-24 | 05/13/2021 |  |  | 2021-03-24 |  |  | 2021-03-29 | 05/17/2021 | 06/28/2021 | 2021-06-29 |  | garage extension, family extension | 19 | 28 | 0 | 50 | 31 | 81
x | Cypress Creek | 7C | 363 | Linden III | 30 - Craftsman | 03/11/2021 | C.Zobel | 2021-03-15 | 04/04/2021 | 300 |  | 04/06/2021 | 2021-03-29 | 05/19/2021 |  |  | 2021-03-29 |  |  | 2021-04-01 | 05/20/2021 | 06/30/2021 | 2021-07-01 |  | bedroom above garage | 16 | 32 | 0 | 50 | 30 | 80
x | Cypress Creek | 00 | 391 | Carlisle | 30 - Craftsman | 03/21/2021 | C.Zobel | 2021-03-23 | 04/16/2021 | 480 |  | 04/20/2021 | 2021-04-06 | 06/02/2021 |  |  | 2021-04-06 |  |  | 2021-04-09 | 06/07/2021 | 07/08/2021 | 2021-07-09 |  |  | 19 | 32 | 0 | 55 | 24 | 79
x | The Parke @ Cypress Creek | 1 | 73 | Stamford | 35 - Cottage | 03/22/2021 | C.Zobel | 2021-03-24 | 04/08/2021 | 300 |  | 04/09/2021 | 2021-04-07 | 05/19/2021 |  |  | 2021-04-07 |  |  | 2021-04-12 | 05/21/2021 | 07/09/2021 | 2021-07-12 |  | storage above garage; generator | 13 | 29 | 0 | 44 | 36 | 80
x | The Parke @ Cypress Creek | 1 | 65 | Easton | 10 - Traditional | 03/25/2021 | C.Zobel | 2021-03-29 | 04/26/2021 | 360 |  | 04/26/2021 | 2021-04-12 | 06/02/2021 |  |  | 2021-04-12 |  |  | 2021-04-15 | 06/07/2021 | 07/14/2021 | 2021-07-15 |  | zero entry garage, add bathroom; generator | 22 | 28 | 0 | 52 | 28 | 80
x | Readers Branch | 2 | 33 | Linden Terrace | 30 - Craftsman | 03/25/2021 | C.Zobel | 2021-03-29 | 05/21/2021 | 480 |  | 05/25/2021 | 2021-04-12 | 06/07/2021 |  |  | 2021-04-12 |  |  | 2021-04-15 | 06/08/2021 | 07/01/2021 | 2021-07-02 |  |  | 41 | 10 | 0 | 53 | 18 | 71
x | Cypress Creek | 7C | 357 | Hartford II | A - European | 04/11/2021 | C.Zobel | 2021-04-13 | 04/30/2021 | 300 |  | 05/07/2021 | 2021-04-27 | 06/18/2021 |  |  | 2021-04-27 |  |  | 2021-04-30 | 06/18/2021 | 07/19/2021 | 2021-07-20 |  |  | 14 | 31 | 0 | 49 | 22 | 71
x | Cypress Creek | 7C | 364 | Carlisle | 30 - Craftsman | 04/11/2021 | C.Zobel | 2021-04-13 | 05/07/2021 | 300 |  | 05/14/2021 | 2021-04-27 | 06/10/2021 |  |  | 2021-04-27 |  |  | 2021-04-30 | 06/14/2021 | 07/21/2021 | 2021-07-22 |  | attic | 19 | 20 | 0 | 45 | 28 | 73
x | Readers Branch | 3 | 12 | Carlisle | 15 - Arts & Crafts | 04/24/2021 | C.Zobel | 2021-04-27 | 05/25/2021 | 180 |  | 05/25/2021 | 2021-05-11 | 06/01/2021 |  |  | 2021-05-11 |  |  | 2021-05-14 | 06/02/2021 | 06/28/2021 | 2021-06-29 |  |  | 21 | 6 | 0 | 27 | 19 | 46
x | Lauradell | 1 | 117 | Savannah | B - Craftsman | 04/25/2021 | C.Zobel | 2021-04-27 | 05/12/2021 | 300 |  | 05/14/2021 | 2021-05-11 | 05/18/2021 |  |  | 2021-05-11 |  |  | 2021-05-14 | 05/19/2021 | 06/30/2021 | 2021-07-01 |  | 2ft rear extension, serenity bath, screened porch | 12 | 3 | 0 | 17 | 31 | 48
x | Lauradell | 1 | 144 | Helena | 30 - Craftsman | 04/30/2021 | C.Zobel | 2021-05-04 | 06/23/2021 | 240 |  | 06/24/2021 | 2021-05-18 | 07/07/2021 |  |  | 2021-05-18 |  |  | 2021-05-21 | 07/12/2021 | 08/03/2021 | 2021-08-04 |  |  | 38 | 10 | 0 | 51 | 17 | 68
x | Readers Branch | 3 | 57 | Corvallis | 40 - European | 04/30/2021 | C.Zobel | 2021-05-04 | 06/16/2021 | 240 |  | 06/16/2021 | 2021-05-18 | 06/22/2021 |  |  | 2021-05-18 |  |  | 2021-05-21 | 06/23/2021 | 07/14/2021 | 2021-07-15 |  | 2fl | 33 | 5 | 0 | 38 | 16 | 54
x | Ford's Colony | 3 | 274 | Hartford II | BSE - Arts & Crafts | 05/10/2021 | C.Zobel | 2021-05-12 | 06/09/2021 | 420 |  | 06/10/2021 | 2021-05-26 | 06/21/2021 |  |  | 2021-05-26 |  |  | 2021-05-31 | 07/27/2021 | 12/15/2021 | 2021-12-16 |  |  | 22 | 8 | 0 | 56 | 102 | 158
x | Lauradell | 1 | 121 | Hadley | 25 - Folk Victorian | 05/15/2021 | C.Zobel | 2021-05-18 | 06/24/2021 | 180 |  | 06/25/2021 | 2021-06-01 | 07/07/2021 |  |  | 2021-06-01 |  |  | 2021-06-04 | 07/09/2021 | 08/03/2021 | 2021-08-04 |  |  | 28 | 9 | 0 | 39 | 18 | 57
x | Readers Branch | 3 | 4 | Linden III | 25 - Folk Victorian | 06/05/2021 | C.Zobel | 2021-06-08 | 07/07/2021 | 240 |  | 07/07/2021 | 2021-06-22 | 07/13/2021 |  |  | 2021-06-22 |  |  | 2021-06-25 | 07/20/2021 | 08/10/2021 | 2021-08-11 |  |  | 22 | 5 | 0 | 31 | 16 | 47
x | Cypress Creek | 7C | 340 | Carlisle | 30 - Craftsman | 06/18/2021 | C.Zobel | 2021-06-22 | 06/29/2021 | 300 |  | 06/29/2021 | 2021-07-06 | 07/08/2021 |  |  | 2021-07-06 |  |  | 2021-07-09 | 07/19/2021 | 08/25/2021 | 2021-08-26 |  |  | 7 | 8 | 0 | 21 | 28 | 49
x | Cypress Creek | 7C | 360 | Savannah | B - Craftsman | 06/28/2021 | C.Zobel | 2021-06-30 | 07/15/2021 | 360 |  | 07/15/2021 | 2021-07-14 | 08/02/2021 |  |  | 2021-07-14 |  |  | 2021-07-19 | 08/03/2021 | 10/7/2021 | 2021-10-08 |  |  | 13 | 13 | 0 | 26 | 48 | 74
x | Readers Branch | 3 | 30 | Fulton | BSE - Arts & Crafts | 06/29/2021 | C.Zobel | 2021-07-01 | 07/13/2021 | 240 |  | 07/13/2021 | 2021-07-15 | 07/20/2021 |  |  | 2021-07-15 |  |  | 2021-07-20 | 07/26/2021 | 08/10/2021 | 2021-08-11 |  |  | 10 | 6 | 0 | 19 | 12 | 31
x | Lauradell | 1 | 123 | Hartford II | BSE - Arts & Crafts | 06/29/2021 | C.Zobel | 2021-07-01 | 07/08/2021 | 240 |  | 07/09/2021 | 2021-07-15 | 07/28/2021 |  |  | 2021-07-15 |  |  | 2021-07-20 | 07/28/2021 | 08/12/2021 | 2021-08-13 |  |  | 7 | 14 | 0 | 21 | 12 | 33
x | Readers Branch | 3 | 47 | Corvallis | 40 - European | 07/09/2021 | C.Zobel | 2021-07-13 | 07/16/2021 | 420 |  | 07/16/2021 | 2021-07-27 | 07/19/2021 |  |  | 2021-07-27 |  |  | 2021-07-30 | 07/21/2021 | 08/23/2021 | 2021-08-24 |  | zero entry | 5 | 2 | 0 | 8 | 24 | 32
x | Readers Branch | 3 | 51 | Linden III | 25 - Folk Victorian | 07/12/2021 | C.Zobel | 2021-07-14 | 07/23/2021 | 360 |  | 07/23/2021 | 2021-07-28 | 07/29/2021 |  |  | 2021-07-28 |  |  | 2021-08-02 | 07/30/2021 | 08/30/2021 | 2021-08-31 |  | extra morning room | 9 | 5 | 0 | 14 | 22 | 36
x | Lauradell | 1 | 142 | Helena | 30 - Craftsman | 07/25/2021 | C.Zobel | 2021-07-27 | 08/13/2021 | 240 |  | 08/17/2021 | 2021-08-10 | 08/23/2021 |  |  | 2021-08-10 |  |  | 2021-08-13 | 08/24/2021 | 09/20/2021 | 2021-09-21 |  |  | 14 | 5 | 0 | 21 | 20 | 41
x | Readers Branch | 3 | 11 | Linden III | 30 - Craftsman | 07/30/2021 | C.Zobel | 2021-08-03 | 09/07/2021 | 180 |  | 09/08/2021 | 2021-08-17 | 09/15/2021 |  |  | 2021-08-17 |  |  | 2021-08-20 | 09/16/2021 | 10/13/2021 | 2021-10-14 |  |  | 27 | 6 | 0 | 34 | 20 | 54
x | Lankford Crossing | 2 | 21 | Hartford II | B - Craftsman | 07/30/2021 | C.Zobel | 2021-08-03 | 08/24/2021 | 300 |  | 08/26/2021 | 2021-08-17 | 09/01/2021 |  |  | 2021-08-17 |  |  | 2021-08-20 | 09/09/2021 | 09/28/2021 | 2021-09-29 |  |  | 17 | 5 | 0 | 29 | 14 | 43
x | Lauradell | 1 | 120 | Linden III | 30 - Craftsman | 07/30/2021 | C.Zobel | 2021-08-03 | 08/30/2021 | 360 |  | 09/02/2021 | 2021-08-17 | 09/07/2021 |  |  | 2021-08-17 |  |  | 2021-08-20 | 09/09/2021 | 09/28/2021 | 2021-09-29 |  | attic above garage; custom screened porch / deck | 21 | 4 | 0 | 29 | 14 | 43
x | The Parke @ Cypress Creek | 1 | 114 | Corvallis | 30 - Craftsman | 08/29/2021 | C.Zobel | 2021-08-31 | 09/14/2021 | 480 |  | 09/16/2021 | 2021-09-14 | 10/22/2021 |  |  | 2021-09-14 |  |  | 2021-09-17 | 10/27/2021 | 12/06/2021 | 2021-12-07 |  | custom front porch, bay window | 11 | 27 | 0 | 42 | 29 | 71
x | Lauradell | 1 | 126 | Helena | 30 - Craftsman | 08/29/2021 | C.Zobel | 2021-08-31 | 09/23/2021 | 300 |  | 09/24/2021 | 2021-09-14 | 09/27/2021 |  |  | 2021-09-14 |  |  | 2021-09-17 | 10/05/2021 | 11/08/2021 | 2021-11-09 |  | alt. drop zone | 18 | 2 | 0 | 26 | 25 | 51
x | Readers Branch | 3 | 68 | Fulton | B - Folk Victorian | 09/13/2021 | C.Zobel | 2021-09-15 | 10/18/2021 | 300 |  | 10/18/2021 | 2021-09-29 | 10/20/2021 |  |  | 2021-09-29 |  |  | 2021-10-04 | 10/22/2021 | 11/22/2021 | 2021-11-23 |  | custom elevation, stoop | 25 | 3 | 0 | 29 | 22 | 51
x | Lauradell | 1 | 102 | Savannah | B - Craftsman | 09/19/2021 | C.Zobel | 2021-09-21 | 10/20/2021 | 240 |  | 10/20/2021 | 2021-10-05 | 10/22/2021 |  |  | 2021-10-05 |  |  | 2021-10-08 | 11/04/2021 | 12/02/2021 | 2021-12-03 |  |  | 22 | 3 | 0 | 33 | 21 | 54
| Givens Farm | 12 | 114 | Savannah | Folk Victorian | 09/21/2021 | C.Zobel | 2021-09-23 | 10/17/2021 | 600 |  | 10/18/2021 | 2021-10-07 | 10/27/2021 |  |  | 2021-10-07 |  |  | 2021-10-12 | 11/05/2021 |  | 1900-01-01 |  | basement, lanai | 18 | 8 | 0 | 33 | -31790 | -31757
x | Readers Branch | 3 | 23 | Fulton Terrace | A - Colonial | 09/24/2021 | C.Zobel | 2021-09-28 | 10/29/2021 | 600 |  | 11/02/2021 | 2021-10-12 | 11/12/2021 |  |  | 2021-10-12 |  |  | 2021-10-15 | 11/17/2021 | 12/15/2021 | 2021-12-16 |  | basement screened porch | 25 | 9 | 0 | 38 | 21 | 59
| Readers Branch | 3 | 23 | Fulton Terrace |  | 09/24/2021 | C.Zobel | 2021-09-28 | 11/02/2021 |  |  | 2021-11-02 | 2021-10-12 | 11/12/2021 |  | 11/02/2021 | 2021-10-12 | 11/08/2021 |  | 2021-10-15 | 11/18/2021 | 12/13/2021 | 2021-12-14 |  |  | 27 | 9 | 5 | 39 | 18 | 57
x | The Parke @ Cypress Creek | 1 | 148 | Stamford | 60 - Farmhouse | 10/08/2021 | C.Zobel | 2021-10-12 | 10/26/2021 | 300 |  | 10/27/2021 | 2021-10-26 | 11/19/2021 |  |  | 2021-10-26 |  |  | 2021-10-29 | 11/29/2021 | 01/04/2022 | 2022-01-05 |  | custom bathroom, corner pantry | 12 | 18 | 0 | 36 | 27 | 63
| Givens Farm | 12 | 130 | Bradford |  | 2021-10-15 | R.Arias | 2021-10-19 | 11/22/2021 |  |  | 2021-11-22 | 2021-11-02 | 12/03/2021 |  | 11/22/2021 | 2021-11-02 | 12/10/2021 |  | 2021-11-05 | 12/20/2021 |  | 1900-01-01 |  |  | 26 | 10 | 15 | 46 | -31821 | -31775
x | Lauradell | 1 | 134 | Savannah | A - Folk Victorian | 10/21/2021 | C.Zobel | 2021-10-25 | 11/11/2021 | 300 |  | 11/15/2021 | 2021-11-08 | 11/16/2021 |  |  | 2021-11-08 |  |  | 2021-11-11 | 11/17/2021 | 01/10/2022 | 2022-01-11 |  | alt second floor, additional bathroom | 15 | 2 | 0 | 19 | 39 | 58
| Givens Farm | 12 | 108 | Savannah | Craftsman | 2021-11-03 | C.Zobel | 2021-11-05 | 11/19/2021 | 240 |  | 11/22/2021 | 2021-11-19 | 12/14/2021 |  |  | 2021-11-19 |  |  | 2021-11-24 | 12/17/2021 |  | 1900-01-01 |  |  | 12 | 17 | 0 | 32 | -31820 | -31788
| Givens Farm | 12 | 105 | Corvallis |  | 11/08/2021 | R.Arias | 2021-11-10 | 12/03/2021 |  |  | 2021-12-03 | 2021-11-24 | 12/14/2021 |  | 12/03/2021 | 2021-11-24 | 12/21/2021 |  | 2021-11-29 |  |  | 1900-01-01 |  |  | 19 | 8 | 13 | -31792 | 0 | -31791
| Lauradell | 1 | 129 | Raleigh | Arts & Crafts B | 11/10/2021 | C.Zobel | 2021-11-12 | 11/30/2021 | 240 |  | 12/01/2021 | 2021-11-26 | 12/03/2021 |  |  | 2021-11-26 |  |  | 2021-12-01 | 12/07/2021 | 2022-01-18 | 2022-01-19 |  |  | 14 | 3 | 0 | 19 | 31 | 50
| Ginter Park | 1 | 4 | Raleigh | Traditional | 2021-11-12 | C.Zobel | 2021-11-16 | 11/22/2021 | 180 |  | 11/23/2021 | 2021-11-30 | 12/01/2021 |  |  | 2021-11-30 |  |  | 2021-12-03 | 12/23/2021 |  | 1900-01-01 |  |  | 6 | 7 | 0 | 29 | -31824 | -31795
| Ginter Park | 1 | 6 | Linden III |  | 2021-11-12 | R.Arias | 2021-11-16 | 11/23/2021 |  |  | 2021-11-23 | 2021-11-30 | 12/01/2021 |  | 11/23/2021 | 2021-11-30 | 01/16/2022 |  | 2021-12-03 |  |  | 1900-01-01 |  |  | 7 | 7 | 39 | -31796 | 0 | -31795
| Ginter Park | 1 | 2 | Linden III |  | 2021-11-12 | R.Arias | 2021-11-16 | 11/23/2021 |  |  | 2021-11-23 | 2021-11-30 | 12/01/2021 |  | 11/23/2021 | 2021-11-30 | 01/06/2022 |  | 2021-12-03 |  |  | 1900-01-01 |  |  | 7 | 7 | 33 | -31796 | 0 | -31795
| Ginter Park | 1 | 3 | Savannah | Folk Victorian | 2021-11-12 | C.Zobel | 2021-11-16 | 12/07/2021 | 240 |  | 12/08/2021 | 2021-11-30 | 12/13/2021 |  |  | 2021-11-30 |  |  | 2021-12-03 | 12/27/2021 |  | 1900-01-01 |  |  | 17 | 4 | 0 | 31 | -31826 | -31795
| Readers Branch | 3 | 6 | Caroline |  | 11/17/2021 | R.Arias | 2021-11-19 | 12/09/2021 |  |  | 2021-12-09 | 2021-12-03 | 12/14/2021 |  | 12/09/2021 | 2021-12-03 | 12/10/2021 |  | 2021-12-08 | 12/16/2021 | 01/12/2022 | 2022-01-13 |  |  | 16 | 4 | 2 | 21 | 20 | 41
| Givens Farm | 12 | 95 | Linden III | Craftsman | 2021-11-18 | Y.Wang | 2021-11-22 | 2020-08-18 | 430 |  | 08/18/2020 | 2021-12-06 | 09/04/2020 |  |  | 2021-12-06 |  |  | 2021-12-09 | 09/04/2020 | 09/07/2020 | 2020-09-08 |  |  | -329 | 14 | 0 | -316 | 2 | -314
| Harpers Mill | 6 | 28 | Hartford II | Arts & Crafts | 11/18/2021 | C.Zobel | 2021-11-22 | 01/03/2022 | 360 |  | 01/05/2022 | 2021-12-06 | 2022-01-13 |  |  | 2021-12-06 |  |  | 2021-12-09 |  |  | 1900-01-01 |  | primary bed bay window, custom guest bed / dining layout | 32 | 7 | 0 | -31800 | 0 | -31799
| Harpers Mill | 6 | 28 | Hartford II |  | 11/18/2021 | C.Zobel | 2021-11-22 | 01/05/2022 |  |  | 2022-01-05 | 2021-12-06 | 2022-01-13 |  |  | 2021-12-06 |  |  | 2021-12-09 |  |  | 1900-01-01 |  |  | 34 | 7 | 0 | -31800 | 0 | -31799
| Harpers Mill | 6 | 20 | Corvallis |  | 11/18/2021 | R.Arias | 2021-11-22 | 01/07/2022 |  |  | 2022-01-07 | 2021-12-06 | 2022-01-14 |  |  | 2021-12-06 |  |  | 2021-12-09 |  |  | 1900-01-01 |  |  | 36 | 6 | 0 | -31800 | 0 | -31799
| Readers Branch | 4 | 5 | Fulton Terrace | Arts & Crafts | 11/18/2021 | C.Zobel | 2021-11-22 | 12/29/2021 | 480 | HBS | 12/30/2021 | 2021-12-06 | 01/10/2022 | Bolen | 2021-12-30 | 2021-12-06 | 2022-01-06 |  | 2021-12-09 | 01/12/2022 |  | 1900-01-01 |  | triple sliding door, CMU basement w/ framed wall, double sided interior fireplace, sewage ejection system | 29 | 8 | 6 | 39 | -31838 | -31799
| Harpers Mill | 6 | 37 | Hartford II | Craftsman | 11/19/2021 | C.Zobel | 2021-11-23 | 01/07/2022 | 240 |  | 01/07/2022 | 2021-12-07 | 2022-01-14 |  |  | 2021-12-07 |  |  | 2021-12-10 |  |  | 1900-01-01 |  |  | 35 | 6 | 0 | -31801 | 0 | -31800
| Harpers Mill | 6 | 36 | Corvallis |  | 11/20/2021 | R.Arias | 2021-11-23 | 01/12/2022 |  |  | 2022-01-12 | 2021-12-07 |  |  |  | 2021-12-07 |  |  | 2021-12-10 |  |  | 1900-01-01 |  |  | 37 | -31838 | 0 | -31801 | 0 | -31800
| Cypress Creek | 7B | 320 | Wellington II |  | 11/20/2021 | R.Arias | 2021-11-23 | 12/08/2021 |  |  | 2021-12-08 | 2021-12-07 | 12/29/2021 |  | 12/08/2021 | 2021-12-07 | 12/09/2021 |  | 2021-12-10 | 01/07/2022 |  | 1900-01-01 |  |  | 12 | 16 | 2 | 34 | -31835 | -31800
| Harpers Mill | 6 | 35 | Hartford II |  | 11/22/2021 | C.Zobel | 2021-11-24 |  |  |  |  | 2021-12-08 |  |  |  | 2021-12-08 |  |  | 2021-12-13 |  |  | 1900-01-01 |  |  | -31802 | 0 | 0 | -31802 | 0 | -31801
| Harpers Mill | 6 | 29 | Fulton |  | 11/23/2021 | R.Arias | 2021-11-25 |  |  |  |  | 2021-12-09 |  |  |  | 2021-12-09 |  |  | 2021-12-14 |  |  | 1900-01-01 |  |  | -31803 | 0 | 0 | -31803 | 0 | -31802
| Readers Branch | 4 | 39 | Carlisle | Arts & Crafts | 11/27/2021 | C.Zobel | 2021-11-30 | 12/30/2021 | 300 |  | 12/31/2021 | 2021-12-14 |  |  |  | 2021-12-14 |  |  | 2021-12-17 |  |  | 1900-01-01 |  | extended family room | 23 | -31830 | 0 | -31806 | 0 | -31805
| Lauradell | 1 | 42 | Manchester |  | 11/29/2021 | R.Arias | 2021-12-01 | 12/28/2021 |  |  | 2021-12-28 | 2021-12-15 | 01/10/2022 |  | 12/28/2021 | 2021-12-15 | 12/30/2021 |  | 2021-12-20 | 1/11/2022 |  | 1900-01-01 |  |  | 21 | 10 | 3 | 31 | -31837 | -31806
| Lauradell | 1 | 116 | Linden III |  | 11/29/2021 | R.Arias | 2021-12-01 | 12/29/2021 |  | Struc Tech | 2021-12-29 | 2021-12-15 | 01/10/2022 | Cardinal | 12/29/2021 | 2021-12-15 | 01/04/2022 |  | 2021-12-20 | 01/10/2022 |  | 1900-01-01 |  | waiting on recordation | 22 | 9 | 5 | 30 | -31836 | -31806
| Row at Westhampton | 1 | 1-7 |  |  | 2021-11-30 | Y.Wang | 2021-12-02 | 2021-11-29 | 1500 | HBS | 2021-12-06 | 2021-12-16 | 2022-01-07 | Koontz | 2021-12-23 | 2021-12-16 | 2022-01-17 |  | 2021-12-21 | 2022-01-18 |  | 1900-01-01 |  |  | -3 | 25 | 18 | 35 | -31842 | -31807
| Row at Westhampton | 1 | 8-14 |  |  | 2021-11-30 | Y.Wang | 2021-12-02 | 2021-11-29 | 1500 | HBS | 2021-12-06 | 2021-12-16 | 2022-01-07 | Koontz | 2021-12-23 | 2021-12-16 |  |  | 2021-12-21 |  |  | 1900-01-01 |  |  | -3 | 25 | -31824 | -31808 | 0 | -31807
| Ginter Park | 1 | 1 | Savannah | Arts & Crafts | 2021-12-03 | C.Zobel | 2021-12-07 | 12/09/2021 | 240 |  | 12/09/2021 | 2021-12-21 | 12/15/2021 |  |  | 2021-12-21 |  |  | 2021-12-24 | 12/23/2021 |  | 1900-01-01 |  |  | 4 | 5 | 0 | 14 | -31824 | -31810
| Lauradell | 1 | 114 | Hartford II | Arts & Crafts | 2021-12-08 | C.Zobel | 2021-12-10 | 12/02/2021 | 240 |  | 12/03/2021 | 2021-12-24 | 12/06/2021 |  |  | 2021-12-24 |  |  | 2021-12-29 | 12/07/2021 | 2022-01-18 | 2022-01-19 |  |  | -6 | 2 | 0 | -3 | 31 | 30
| Harpers Mill | 6 | 26 | Belmont |  | 12/09/2021 | R.Arias | 2021-12-13 |  |  |  |  | 2021-12-27 |  |  |  | 2021-12-27 |  |  | 2021-12-30 |  |  | 1900-01-01 |  |  | -31815 | 0 | 0 | -31815 | 0 | -31814
| Readers Branch | 3 | 49 | Fulton | Art & Crafts | 2021-12-10 | C.Zobel | 2021-12-14 | 2022-01-03 | 360 | Struc Tech | 12/13/2021 | 2021-12-28 | 12/15/2021 | Cardinal |  | 2021-12-28 |  |  | 2021-12-31 | 12/27/2021 |  | 1900-01-01 |  | waiting on recordation; primary bed bay window, custom guest bed / dining layout | 16 | 3 | 0 | 11 | -31826 | -31815
| Readers Branch | 4 | 36 | Corvallis | Colonial | 2021-12-10 | C.Zobel | 2021-12-14 | 10/20/2021 | 180 |  | 10/21/2021 | 2021-12-28 | 10/25/2021 |  |  | 2021-12-28 |  |  | 2021-12-31 | 12/14/2021 |  | 1900-01-01 |  | attic w/ pull-down, extended WIC & laundry, laundry pocket door | -39 | 3 | 0 | 2 | -31817 | -31815
| Ginter Park | 1 | 5 | Savannah | Folk Victorian | 2021-12-10 | C.Zobel | 2021-12-14 | 11/12/2021 | 360 |  | 12/15/2021 | 2021-12-28 | 12/17/2021 |  |  | 2021-12-28 |  |  | 2021-12-31 | 12/23/2021 |  | 1900-01-01 |  | custom second floor, custom first floor, screened porch, NanaWall (on first draft) | -22 | 3 | 0 | 9 | -31824 | -31815
| Lauradell | 1 | 139 | Helena | Craftsman | 2021-12-10 | C.Zobel | 2021-12-14 | 12/11/2021 | 240 |  | 12/13/2021 | 2021-12-28 | 12/15/2021 |  |  | 2021-12-28 |  |  | 2021-12-31 | 12/27/2021 |  | 1900-01-01 |  |  | 0 | 3 | 0 | 11 | -31826 | -31815
| Givens Farm | 12 | 129 | Hartford II | BSE - Arts & Crafts | 12/14/2021 | C.Zobel | 2021-12-16 | 2022-01-14 | 150 | Riverside |  | 2021-12-30 |  |  |  | 2021-12-30 |  |  | 2022-01-04 |  |  | 1900-01-01 |  | lifestyle selections not complete | 23 | 0 | 0 | -31818 | 0 | -31817
| Harpers Mill | 6 | 30 | Corvallis |  | 12/16/2021 | R.Arias | 2021-12-20 |  |  | Struc Tech |  | 2022-01-03 | 2022-01-12 | Bolen | 2021-12-31 | 2022-01-03 | 2022-01-06 |  | 2022-01-06 |  |  | 1900-01-01 |  |  | -31820 | 31838 | 5 | -31820 | 0 | -31819
| Lauradell | 1 | 145 | Hawthorne |  | 12/18/2021 | R.Arias | 2021-12-21 | 01/10/2022 |  |  | 2022-01-10 | 2022-01-04 | 2022-01-14 |  | 01/10/2022 | 2022-01-04 | 2022-01-17 |  | 2022-01-07 | 2022-01-18 |  | 1900-01-01 |  |  | 15 | 5 | 6 | 21 | -31842 | -31820
| Lankford Crossing | 2 | 39 | Savannah | Arts & Crafts | 2021-12-20 | C.Zobel | 2021-12-22 | 01/05/2022 | 240 |  | 01/06/2022 | 2022-01-05 |  |  |  | 2022-01-05 |  |  | 2022-01-10 |  |  | 1900-01-01 |  |  | 12 | -31834 | 0 | -31822 | 0 | -31821
| Lankford Crossing | 3 | 4 | Hartford II | Craftsman | 2021-12-20 | C.Zobel | 2021-12-22 | 01/12/2022 | 240 | Struc Tech |  | 2022-01-05 |  | Koontz | 2022-01-06 | 2022-01-05 | 2022-01-17 |  | 2022-01-10 |  |  | 1900-01-01 |  |  | 17 | 0 | 8 | -31822 | 0 | -31821
| Lauradell | 1 | 128 | Hartford II |  | 12/22/2021 | R.Arias | 2021-12-24 | 01/14/2022 |  |  | 2022-01-14 | 2022-01-07 |  |  | 01/14/2022 | 2022-01-07 | 2022-01-18 |  | 2022-01-12 |  |  | 1900-01-01 |  |  | 17 | -31840 | 3 | -31824 | 0 | -31823
| Readers Branch | 3 | 69 | Fulton |  | 12/23/2021 | R.Arias | 2021-12-27 | 01/12/2022 |  | Struc Tech | 2022-01-13 | 2022-01-10 |  | Koontz | 2022-01-13 | 2022-01-10 |  |  | 2022-01-13 |  |  | 1900-01-01 |  | Sent to eng delayed due to incoming delayed structural addendum #2 | 14 | -31839 | -31839 | -31825 | 0 | -31824
| Harpers Mill | 6 | 19 | Belmont |  | 12/23/2021 | R.Arias | 2021-12-27 | 01/12/2022 |  |  | 2022-01-12 | 2022-01-10 | 2022-01-14 |  |  | 2022-01-10 |  |  | 2022-01-13 |  |  | 1900-01-01 |  |  | 14 | 3 | 0 | -31825 | 0 | -31824
| Readers Branch | 3 | 80 | Hadley |  | 12/23/2021 | R.Arias | 2021-12-27 | 1/11/2022 |  |  | 2022-01-11 | 2022-01-10 | 2022-01-14 |  | 1/11/2022 | 2022-01-10 | 1/13/2022 |  | 2022-01-13 | 2022-01-18 |  | 1900-01-01 |  |  | 13 | 4 | 3 | 18 | -31842 | -31824
[5 empty] | Traditional | 2021-12-27 |  | 2021-12-29 | 2022-01-14 | 240 | DFI | 2022-01-17 | 2022-01-12 |  | Hassel | 2022-01-17 | 2022-01-12 |  |  | 2022-01-17 |  |  | 1900-01-01 |  | attached shed | 14 | -31841 | -31841 | -31827 | 0 | -31826
| Cypress Creek | 0 | 229 | Linden III |  | 12/27/2021 | C.Zobel | 2021-12-29 |  |  |  |  | 2022-01-12 |  |  |  | 2022-01-12 |  |  | 2022-01-17 |  |  | 1900-01-01 |  |  | -31827 | 0 | 0 | -31827 | 0 | -31826
| Readers Branch | 4 | 8 | Fulton Terrace |  | 12/28/2021 | C.Zobel | 2021-12-30 |  |  |  |  | 2022-01-13 |  |  |  | 2022-01-13 |  |  | 2022-01-18 |  |  | 1900-01-01 |  |  | -31828 | 0 | 0 | -31828 | 0 | -31827
[5 empty] | Folk Victorian | 2021-12-29 |  | 2021-12-31 | 2022-01-17 | 240 | Struc Tech | 2022-01-17 | 2022-01-14 |  | Bolen | 2022-01-17 | 2022-01-14 |  |  | 2022-01-19 |  |  | 1900-01-01 |  |  | 13 | -31841 | -31841 | -31829 | 0 | -31828
| Lauradell | 1 | 101 | Savannah |  | 12/29/2021 | C.Zobel | 2021-12-31 |  |  |  |  | 2022-01-14 |  |  |  | 2022-01-14 |  |  | 2022-01-19 |  |  | 1900-01-01 |  |  | -31829 | 0 | 0 | -31829 | 0 | -31828
| Readers Branch | 3 | 77 | Fulton |  | 12/30/2021 | R.Arias | 2022-01-03 | 2022-01-15 |  |  | 2022-01-17 | 2022-01-17 |  |  | 2022-01-17 | 2022-01-17 |  |  | 2022-01-20 |  |  | 1900-01-01 |  |  | 11 | -31841 | -31841 | -31830 | 0 | -31829
| Readers Branch | 4 | 15 | Fulton | Arts & Crafts | 12/30/2021 | C.Zobel | 2022-01-03 |  |  |  |  | 2022-01-17 |  | Parker |  | 2022-01-17 |  |  | 2022-01-20 |  |  | 1900-01-01 |  | lifestyle selections not complete; guest bed w/ extended loft, 4 ft rear ext | -31830 | 0 | 0 | -31830 | 0 | -31829
| Lauradell | 1 | 140 | Manchester |  | 01/04/2022 | R.Arias | 2022-01-06 |  |  |  |  | 2022-01-20 |  |  |  | 2022-01-20 |  |  | 2022-01-25 |  |  | 1900-01-01 |  |  | -31833 | 0 | 0 | -31833 | 0 | -31832
| Readers Branch | 3 | 50 | Corvallis |  | 01/07/2022 | R.Arias | 2022-01-11 | 01/10/2022 |  |  | 2022-01-10 | 2022-01-25 | 2022-01-14 |  | 01/10/2022 | 2022-01-25 | 01/12/2022 |  | 2022-01-28 | 1/18/20022 |  | 1900-01-01 |  |  | 1 | 5 | 3 | #VALUE! | #VALUE! | -31835
| Lauradell | 1 | 125 | Savannah |  | 01/09/2022 | C.Zobel | 2022-01-11 |  |  |  |  | 2022-01-25 |  |  |  | 2022-01-25 |  |  | 2022-01-28 |  |  | 1900-01-01 |  |  | -31836 | 0 | 0 | -31836 | 0 | -31835
| Lauradell | 1 | 138 | Hawthorne |  | 2022-01-13 | R.Arias | 2022-01-17 |  |  | Struc Tech |  | 2022-01-31 |  |  |  | 2022-01-31 |  |  | 2022-02-03 |  |  | 1900-01-01 |  |  | -31840 | 0 | 0 | -31840 | 0 | -31839
| Lauradell | 1 | 138 | Hawthorne |  | 01/13/2022 | R.Arias | 2022-01-17 |  |  |  |  | 2022-01-31 |  |  |  | 2022-01-31 |  |  | 2022-02-03 |  |  | 1900-01-01 |  |  | -31840 | 0 | 0 | -31840 | 0 | -31839
| Readers Branch | 4 | 6 | Hartford Terrace |  | 2022-01-13 | C.Zobel | 2022-01-17 |  |  | HBS |  | 2022-01-31 |  |  |  | 2022-01-31 |  |  | 2022-02-03 |  |  | 1900-01-01 |  |  | -31840 | 0 | 0 | -31840 | 0 | -31839
| The Meadows | 0 | 53 | Westfield |  | 01/14/2022 | R.Arias | 2022-01-18 | 2022-01-15 |  |  | 2022-01-17 | 2022-02-01 |  |  | 2022-01-17 | 2022-02-01 |  |  | 2022-02-04 |  |  | 1900-01-01 |  |  | 0 | -31841 | -31841 | -31841 | 0 | -31840
| The Meadows | 0 | 56 | Carlisle |  | 01/14/2022 | C.Zobel | 2022-01-18 |  |  |  |  | 2022-02-01 |  |  |  | 2022-02-01 |  |  | 2022-02-04 |  |  | 1900-01-01 |  |  | -31841 | 0 | 0 | -31841 | 0 | -31840
| The Meadows | 0 | 54 | Westminster |  | 01/14/2022 | R.Arias | 2022-01-18 |  |  | Riverside |  | 2022-02-01 |  |  |  | 2022-02-01 |  |  | 2022-02-04 |  |  | 1900-01-01 |  |  | -31841 | 0 | 0 | -31841 | 0 | -31840
| The Meadows | 0 | 55 | Bradford |  | 01/14/2022 | R.Arias | 2022-01-18 |  |  | Riverside |  | 2022-02-01 |  |  |  | 2022-02-01 |  |  | 2022-02-04 |  |  | 1900-01-01 |  |  | -31841 | 0 | 0 | -31841 | 0 | -31840
| Lauradell | 1 | 132 | Helena |  | 2022-01-15 | R.Arias | 2022-01-18 |  |  | Struc Tech |  | 2022-02-01 |  |  |  | 2022-02-01 |  |  | 2022-02-04 |  |  | 1900-01-01 |  |  | -31841 | 0 | 0 | -31841 | 0 | -31840
| Readers Branch | 4 | 44 | Fulton |  | 2022-01-17 | C.Zobel | 2022-01-19 |  |  | Struc Tech |  | 2022-02-02 |  |  |  | 2022-02-02 |  |  | 2022-02-07 |  |  | 1900-01-01 |  |  | -31842 | 0 | 0 | -31842 | 0 | -31841
| Harpers Mill | 6 | 27 | Hadley |  | 2022-01-18 | R.Arias | 2022-01-20 |  |  | Struc Tech |  | 2022-02-03 |  |  |  | 2022-02-03 |  |  | 2022-02-08 |  |  | 1900-01-01 |  |  | -31843 | 0 | 0 | -31843 | 0 | -31842
| Cypress Creek | 7B | 318 | Linden III |  | 2022-01-18 | C.Zobel | 2022-01-20 |  |  | DFI |  | 2022-02-03 |  |  |  | 2022-02-03 |  |  | 2022-02-08 |  |  | 1900-01-01 |  |  | -31843 | 0 | 0 | -31843 | 0 | -31842
| Cypress Creek | 7B | 319 | Savannah |  | 2022-01-18 | R.Arias | 2022-01-20 |  |  | DFI |  | 2022-02-03 |  |  |  | 2022-02-03 |  |  | 2022-02-08 |  |  | 1900-01-01 |  |  | -31843 | 0 | 0 | -31843 | 0 | -31842
x | Lauradell | 1 | 13 | Raleigh | 40 - Arts & Crafts B | MODEL | C.Zobel | #VALUE! | 2020-03-17 | 300 |  | 03/17/2020 | #VALUE! | 03/24/2020 |  |  | #VALUE! |  |  | #VALUE! | 04/24/2020 | 05/08/2020 | 2020-05-11 |  | sales center | #VALUE! | 6 | 0 | #VALUE! | 11 | #VALUE!
x | The Parke @ Cypress Creek | 1 | 62 | Stamford | 70 - Coastal | MODEL | C.Zobel | #VALUE! | 01/28/2021 | 300 |  | 01/29/2021 | #VALUE! | 02/15/2021 |  |  | #VALUE! |  |  | #VALUE! | 03/01/2021 | 04/26/2021 | 2021-04-27 |  |  | #VALUE! | 12 | 0 | #VALUE! | 41 | #VALUE!
x | Lauradell | 1 | 136 | Helena | 30 - Craftsman | MODEL | C.Zobel | #VALUE! | 03/18/2021 | 480 |  | 03/23/2021 | #VALUE! | 03/25/2021 |  |  | #VALUE! |  |  | #VALUE! | 04/14/2021 | 04/30/2021 | 2021-05-03 |  | sales center | #VALUE! | 3 | 0 | #VALUE! | 13 | #VALUE!
x | GreenGate |  | 078 | Rowland | GR - B - 2 - R | SPEC | Y.Wang | #VALUE! | 2018-11-16 | 720 |  | 12/10/2018 | #VALUE! | 2018-12-31 |  |  | #VALUE! |  |  | #VALUE! | 01/22/2019 | 2019-02-07 | 2019-02-08 |  |  | #VALUE! | 16 | 0 | #VALUE! | 13 | #VALUE!
x | GreenGate |  | 079 | Park | QA - D - 2 - F | SPEC | Y.Wang | #VALUE! | 2018-11-16 | 720 |  | 12/10/2018 | #VALUE! | 2018-12-31 |  |  | #VALUE! |  |  | #VALUE! | 01/22/2019 | 2019-02-07 | 2019-02-08 |  |  | #VALUE! | 16 | 0 | #VALUE! | 13 | #VALUE!
x | GreenGate |  | 080 | Park | GE - C - 2 - R | SPEC | Y.Wang | #VALUE! | 2018-11-16 | 720 |  | 12/10/2018 | #VALUE! | 2018-12-31 |  |  | #VALUE! |  |  | #VALUE! | 01/22/2019 | 2/7/2019 | 2019-02-08 |  |  | #VALUE! | 16 | 0 | #VALUE! | 13 | #VALUE!
x | GreenGate |  | 081 | Park | QA - B - 2 - F | SPEC | Y.Wang | #VALUE! | 2018-11-16 | 720 |  | 12/10/2018 | #VALUE! | 2018-12-31 |  |  | #VALUE! |  |  | #VALUE! | 01/22/2019 | 2/7/2019 | 2019-02-08 |  |  | #VALUE! | 16 | 0 | #VALUE! | 13 | #VALUE!
x | GreenGate |  | 082 | Rowland | GE - A - 2 - R | SPEC | Y.Wang | #VALUE! | 2018-11-16 | 720 |  | 12/10/2018 | #VALUE! | 2018-12-31 |  |  | #VALUE! |  |  | #VALUE! | 01/22/2019 | 2/7/2019 | 2019-02-08 |  |  | #VALUE! | 16 | 0 | #VALUE! | 13 | #VALUE!
x | Harpers Mill |  | 005 | Linden Terrace | 25 - Folk Victorian | SPEC | N.Blinn | #VALUE! | 2019-01-01 | 240 |  |  | #VALUE! |  |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 0 | 0 | #VALUE! | 0 | #VALUE!
x | John Rolfe Square |  | 019 | Hartford Terrace | 30 - Craftsman | SPEC | R.Arias | #VALUE! | 2019-01-01 | 120 |  |  | #VALUE! |  |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 0 | 0 | #VALUE! | 0 | #VALUE!
x | Culpepper Landing |  | 634 | Manchester |  | SPEC | R.Arias | #VALUE! | 2019-01-06 |  |  |  | #VALUE! |  |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 0 | 0 | #VALUE! | 0 | #VALUE!
x | Culpepper Landing |  | 783 | Wellesley |  | SPEC | R.Arias | #VALUE! | 2019-01-07 |  |  |  | #VALUE! |  |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 0 | 0 | #VALUE! | 0 | #VALUE!
x | John Rolfe Square |  | 030 | Raleigh | 40 - Arts & Crafts B | SPEC | Y.Wang | #VALUE! | 2019-03-01 | 480 |  | 03/01/2019 04/02/2019 | #VALUE! | 03/08/2019 |  |  | #VALUE! |  |  | #VALUE! | 03/08/2019 |  | 1900-01-01 |  | County notes: Front porch must be 6' deep. Re-sent to eng on 04/02. | #VALUE! | #VALUE! | 0 | #VALUE! | -31095 | #VALUE!
x | GreenGate |  | 090 | Westmoreland | GE - E - 1 - R | SPEC | Y.Wang | #VALUE! | 2019-03-15 | 600 |  | 03/15/2019 | #VALUE! | 03/29/2019 |  |  | #VALUE! |  |  | #VALUE! | 04/02/2019 | 5/9/2019 | 2019-05-10 |  |  | #VALUE! | 11 | 0 | #VALUE! | 28 | #VALUE!
x | GreenGate |  | 092 | Rowland | GR - D - 1 - F | SPEC | Y.Wang | #VALUE! | 2019-03-15 | 600 |  | 03/15/2019 | #VALUE! | 03/29/2019 |  |  | #VALUE! |  |  | #VALUE! | 04/02/2019 | 5/9/2019 | 2019-05-10 |  |  | #VALUE! | 11 | 0 | #VALUE! | 28 | #VALUE!
x | GreenGate |  | 094 | Rowland | GE - B - 1 - F | SPEC | Y.Wang | #VALUE! | 2019-03-15 | 600 |  | 03/15/2019 | #VALUE! | 03/29/2019 |  |  | #VALUE! |  |  | #VALUE! | 04/02/2019 | 5/9/2019 | 2019-05-10 |  |  | #VALUE! | 11 | 0 | #VALUE! | 28 | #VALUE!
x | GreenGate |  | 083 | Rowland | QA - A - 2 - F | SPEC | Y.Wang | #VALUE! | 2019-03-28 | 480 |  | 04/02/2019 | #VALUE! | 04/17/2019 |  |  | #VALUE! |  |  | #VALUE! | 04/17/2019 | 5/17/2019 | 2019-05-20 |  |  | #VALUE! | 12 | 0 | #VALUE! | 23 | #VALUE!
x | GreenGate |  | 084 | Park | GE - D - 2 - R | SPEC | Y.Wang | #VALUE! | 2019-03-28 | 480 |  | 04/02/2019 | #VALUE! | 04/17/2019 |  |  | #VALUE! |  |  | #VALUE! | 04/17/2019 | 5/17/2019 | 2019-05-20 |  |  | #VALUE! | 12 | 0 | #VALUE! | 23 | #VALUE!
x | GreenGate |  | 085 | Park | GR - C - 2 - F | SPEC | Y.Wang | #VALUE! | 2019-03-28 | 480 |  | 04/02/2019 | #VALUE! | 04/17/2019 |  |  | #VALUE! |  |  | #VALUE! | 04/17/2019 | 5/17/2019 | 2019-05-20 |  |  | #VALUE! | 12 | 0 | #VALUE! | 23 | #VALUE!
x | GreenGate |  | 086 | Park | GE - B - 2 - F | SPEC | Y.Wang | #VALUE! | 2019-03-28 | 480 |  | 04/02/2019 | #VALUE! | 04/17/2019 |  |  | #VALUE! |  |  | #VALUE! | 04/17/2019 | 5/17/2019 | 2019-05-20 |  |  | #VALUE! | 12 | 0 | #VALUE! | 23 | #VALUE!
x | GreenGate |  | 087 | Park | QA - B - 2 - R | SPEC | Y.Wang | #VALUE! | 2019-03-28 | 480 |  | 04/02/2019 | #VALUE! | 04/17/2019 |  |  | #VALUE! |  |  | #VALUE! | 04/17/2019 | 5/17/2019 | 2019-05-20 |  |  | #VALUE! | 12 | 0 | #VALUE! | 23 | #VALUE!
x | GreenGate |  | 088 | Rowland | GR - D - 2 - F | SPEC | Y.Wang | #VALUE! | 2019-03-28 | 480 |  | 04/02/2019 | #VALUE! | 04/17/2019 |  |  | #VALUE! |  |  | #VALUE! | 04/17/2019 | 5/17/2019 | 2019-05-20 |  |  | #VALUE! | 12 | 0 | #VALUE! | 23 | #VALUE!
x | Readers Branch |  | 014 | Hartford Terrace | 10 - Traditional | SPEC | C.Zobel | #VALUE! | 2019-04-22 | 330 |  | 04/29/2019 | #VALUE! | 2019-05-21 |  |  | #VALUE! |  |  | #VALUE! | 05/23/2019 | 2019-06-28 | 2019-07-01 |  |  | #VALUE! | 17 | 0 | #VALUE! | 27 | #VALUE!
x | Readers Branch |  | 022 | Linden Terrace | 25 - Folk Victorian | SPEC | N.Blinn | #VALUE! | 2019-04-26 |  |  | 06/14/2019 | #VALUE! | 06/27/2019 |  |  | #VALUE! |  |  | #VALUE! | 06/27/2019 | 07/24/2019 | 2019-07-25 |  |  | #VALUE! | 10 | 0 | #VALUE! | 20 | #VALUE!
x | Readers Branch |  | 010 | Belmont Terrace | 10 - Traditional | SPEC | C.Zobel | #VALUE! | 2019-05-29 | 300 |  | 05/30/2019 | #VALUE! | 06/14/2019 |  |  | #VALUE! |  |  | #VALUE! | 06/14/2019 | 07/24/2019 | 2019-07-25 |  |  | #VALUE! | 12 | 0 | #VALUE! | 29 | #VALUE!
x | John Rolfe Square |  | 020 | Linden Terrace | 30 - Craftsman | SPEC | C.Zobel | #VALUE! | 2019-06-26 | 300 |  | 06/27/2019 | #VALUE! | 07/10/2019 |  |  | #VALUE! |  |  | #VALUE! | 07/10/2019 | 08/19/2019 | 2019-08-20 |  |  | #VALUE! | 10 | 0 | #VALUE! | 29 | #VALUE!
x | GreenGate | 3 | 095 | Rowland | QA -B - 1 - F | SPEC | Y.Wang | #VALUE! | 2019-08-12 | 400 |  | 08/12/2019 | #VALUE! | 09/06/2019 |  |  | #VALUE! |  |  | #VALUE! | 09/09/2019 | 10/18/2019 | 2019-10-21 |  |  | #VALUE! | 20 | 0 | #VALUE! | 30 | #VALUE!
x | GreenGate | 3 | 096 | Park | GR - B - 1 - R | SPEC | Y.Wang | #VALUE! | 2019-08-12 | 400 |  | 08/12/2019 | #VALUE! | 09/06/2019 |  |  | #VALUE! |  |  | #VALUE! | 09/09/2019 | 10/18/2019 | 2019-10-21 |  |  | #VALUE! | 20 | 0 | #VALUE! | 30 | #VALUE!
x | GreenGate | 3 | 097 | Park | GE - B - 1 - F | SPEC | Y.Wang | #VALUE! | 2019-08-12 | 400 |  | 08/12/2019 | #VALUE! | 09/06/2019 |  |  | #VALUE! |  |  | #VALUE! | 09/09/2019 | 10/18/2019 | 2019-10-21 |  |  | #VALUE! | 20 | 0 | #VALUE! | 30 | #VALUE!
x | GreenGate | 3 | 098 | Park | QA - C - 1 - F | SPEC | Y.Wang | #VALUE! | 2019-08-12 | 400 |  | 08/12/2019 | #VALUE! | 09/06/2019 |  |  | #VALUE! |  |  | #VALUE! | 09/09/2019 | 10/18/2019 | 2019-10-21 |  |  | #VALUE! | 20 | 0 | #VALUE! | 30 | #VALUE!
x | GreenGate | 3 | 099 | Park | GE - A - 1 - F | SPEC | Y.Wang | #VALUE! | 2019-08-12 | 400 |  | 08/12/2019 | #VALUE! | 09/06/2019 |  |  | #VALUE! |  |  | #VALUE! | 09/09/2019 | 10/18/2019 | 2019-10-21 |  |  | #VALUE! | 20 | 0 | #VALUE! | 30 | #VALUE!
x | GreenGate | 3 | 100 | Park | QA - A - 1 - R | SPEC | Y.Wang | #VALUE! | 2019-08-12 | 400 |  | 08/12/2019 | #VALUE! | 09/06/2019 |  |  | #VALUE! |  |  | #VALUE! | 09/09/2019 | 10/18/2019 | 2019-10-21 |  |  | #VALUE! | 20 | 0 | #VALUE! | 30 | #VALUE!
x | GreenGate | 3 | 101 | Park | GR - A - 1 - F | SPEC | Y.Wang | #VALUE! | 2019-08-12 | 400 |  | 08/12/2019 | #VALUE! | 09/06/2019 |  |  | #VALUE! |  |  | #VALUE! | 09/09/2019 | 10/18/2019 | 2019-10-21 |  |  | #VALUE! | 20 | 0 | #VALUE! | 30 | #VALUE!
x | GreenGate | 3 | 102 | Rowland | GE - C - 1 - F | SPEC | Y.Wang | #VALUE! | 2019-08-12 | 400 |  | 08/12/2019 | #VALUE! | 09/06/2019 |  |  | #VALUE! |  |  | #VALUE! | 09/09/2019 | 10/18/2019 | 2019-10-21 |  |  | #VALUE! | 20 | 0 | #VALUE! | 30 | #VALUE!
x | McRea & Lacy | 2 | 020 | Southaven | —— | SPEC | Y.Wang | #VALUE! | 2019-09-03 | 300 |  | 09/26/2019 | #VALUE! | 12/20/2019 |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 62 | 0 | #VALUE! | 0 | #VALUE!
x | McRae & Lacy | 2 | 021 | Southaven | —— | SPEC | Y.Wang | #VALUE! | 2019-09-03 | 300 |  | 09/26/2019 | #VALUE! | 12/20/2019 |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 62 | 0 | #VALUE! | 0 | #VALUE!
x | McRae & Lacy | 2 | 022 | Southaven | —— | SPEC | Y.Wang | #VALUE! | 2019-09-03 | 300 |  | 09/26/2019 | #VALUE! | 12/20/2019 |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 62 | 0 | #VALUE! | 0 | #VALUE!
x | McRae & Lacy | 2 | 023 | Southaven | —— | SPEC | Y.Wang | #VALUE! | 2019-09-03 | 300 |  | 09/26/2019 | #VALUE! | 12/20/2019 |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 62 | 0 | #VALUE! | 0 | #VALUE!
x | McRae & Lacy | 2 | 024 | Southaven | —— | SPEC | Y.Wang | #VALUE! | 2019-09-03 | 300 |  | 09/26/2019 | #VALUE! | 12/20/2019 |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 62 | 0 | #VALUE! | 0 | #VALUE!
x | McRae & Lacy | 2 | 025 | Southaven | —— | SPEC | Y.Wang | #VALUE! | 2019-09-03 | 300 |  | 09/26/2019 | #VALUE! | 12/20/2019 |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 62 | 0 | #VALUE! | 0 | #VALUE!
x | McRae & Lacy | 2 | 026 | Southaven | —— | SPEC | Y.Wang | #VALUE! | 2019-09-03 | 300 |  | 09/26/2019 | #VALUE! | 12/20/2019 |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 62 | 0 | #VALUE! | 0 | #VALUE!
x | Greengate | 1 | 177 | Davenport | QA-C-1-F | SPEC | Y.Wang | #VALUE! | 2019-09-25 | 300 |  | 09/26/2019 | #VALUE! | 10/24/2019 |  |  | #VALUE! |  |  | #VALUE! | 10/29/2019 | 12/27/2019 | 2019-12-30 |  |  | #VALUE! | 21 | 0 | #VALUE! | 44 | #VALUE!
x | Greengate | 1 | 178 | Davenport | GE-A-1-F | SPEC | Y.Wang | #VALUE! | 2019-09-25 | 300 |  | 09/26/2019 | #VALUE! | 10/24/2019 |  |  | #VALUE! |  |  | #VALUE! | 10/29/2019 | 12/27/2019 | 2019-12-30 |  |  | #VALUE! | 21 | 0 | #VALUE! | 44 | #VALUE!
x | Greengate | 1 | 179 | Davenport | GR-B-1-F | SPEC | Y.Wang | #VALUE! | 2019-09-25 | 300 |  | 09/26/2019 | #VALUE! | 10/24/2019 |  |  | #VALUE! |  |  | #VALUE! | 10/29/2019 | 12/27/2019 | 2019-12-30 |  |  | #VALUE! | 21 | 0 | #VALUE! | 44 | #VALUE!
x | Harpers Mill | 2 | 11 | Hadley | 10 - Traditional | SPEC | C.Zobel | #VALUE! | 2019-10-16 | 120 |  | 10/17/2019 | #VALUE! | 10/22/2019 |  |  | #VALUE! |  |  | #VALUE! | 10/22/2019 | 11/22/2019 | 2019-11-25 |  |  | #VALUE! | 4 | 0 | #VALUE! | 24 | #VALUE!
x | Harpers Mill | 2 | 37 | Hadley | 10 - Traditional | SPEC | C.Zobel | #VALUE! | 2019-10-17 | 45 |  | 10/17/2019 | #VALUE! | 10/23/2019 |  |  | #VALUE! |  |  | #VALUE! | 10/24/2019 | 11/22/2019 | 2019-11-25 |  |  | #VALUE! | 5 | 0 | #VALUE! | 22 | #VALUE!
x | Cypress Creek |  | 413 | Linden III | 30 - Craftsman | SPEC | C.Zobel | #VALUE! | 2019-10-18 | 420 |  | 10/22/2019 | #VALUE! | 11/13/2019 |  |  | #VALUE! |  |  | #VALUE! | 11/14/2019 | 01/29/2020 | 2020-01-30 |  |  | #VALUE! | 17 | 0 | #VALUE! | 55 | #VALUE!
x | Harpers Mill | 4 | 1 | Belmont | 30 - Craftsman | SPEC | C.Zobel | #VALUE! | 2020-01-15 | 120 |  | 01/27/2020 | #VALUE! | 01/29/2020 |  |  | #VALUE! |  |  | #VALUE! | 02/05/2020 | 03/09/2020 | 2020-03-10 |  |  | #VALUE! | 3 | 0 | #VALUE! | 24 | #VALUE!
x | Greengate | 3 | 110 | Rowland | GR - A - 1 - R | SPEC | Y.Wang | #VALUE! | 2020-01-15 | 260 |  | 02/05/2020 | #VALUE! | 02/21/2020 |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 13 | 0 | #VALUE! | 0 | #VALUE!
x | Greengate | 3 | 111 | Park | QA - A - 1 - F | SPEC | Y.Wang | #VALUE! | 2020-01-18 | 260 |  | 02/05/2020 | #VALUE! | 02/21/2020 |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 13 | 0 | #VALUE! | 0 | #VALUE!
x | Greengate | 3 | 112 | Park | GE - B - 1 - F | SPEC | Y.Wang | #VALUE! | 2020-01-20 | 240 |  | 02/05/2020 | #VALUE! | 02/21/2020 |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 13 | 0 | #VALUE! | 0 | #VALUE!
x | Greengate | 3 | 116 | Rowland | GE - C - 1 - F | SPEC | Y.Wang | #VALUE! | 2020-02-05 | 260 |  | 02/05/2020 | #VALUE! | 02/21/2020 |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 13 | 0 | #VALUE! | 0 | #VALUE!
x | Greengate | 3 | 113 | Rowland | QA - B - 1 - F | SPEC | Y.Wang | #VALUE! | 2020-02-05 | 260 |  | 02/05/2020 | #VALUE! | 02/21/2020 |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 13 | 0 | #VALUE! | 0 | #VALUE!
x | Greengate | 3 | 114 | Rowland | GR - D - 1 - F | SPEC | Y.Wang | #VALUE! | 2020-02-05 | 260 |  | 02/05/2020 | #VALUE! | 02/21/2020 |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 13 | 0 | #VALUE! | 0 | #VALUE!
x | Greengate | 3 | 115 | Park | QA - C - 1 - F | SPEC | Y.Wang | #VALUE! | 2020-02-05 | 180 |  | 02/05/2020 | #VALUE! | 02/21/2020 |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 13 | 0 | #VALUE! | 0 | #VALUE!
x | Readers Branch | 2 | 24 | Linden III | 30 - Craftsman | SPEC | C.Zobel | #VALUE! | 2020-02-25 | 165 |  | 02/26/2020 | #VALUE! | 02/28/2020 |  |  | #VALUE! |  |  | #VALUE! | 03/03/2020 | 06/24/2020 | 2020-06-25 |  |  | #VALUE! | 3 | 0 | #VALUE! | 82 | #VALUE!
x | Lake Margaret | 1 | 10 | Hartford Terrace | 10 - Traditional | SPEC | R.Arias | #VALUE! | 2020-03-10 |  |  | 03/10/2020 | #VALUE! |  |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | -31357 | 0 | #VALUE! | 0 | #VALUE!
x | Lake Margaret | 1 | 19 | Linden III | 30 - Craftsman | SPEC | Y.Wang | #VALUE! | 2020-03-10 | 300 |  | 03/10/2020 | #VALUE! | 03/16/2020 |  |  | #VALUE! |  |  | #VALUE! | 03/27/2020 |  | 1900-01-01 |  |  | #VALUE! | 5 | 0 | #VALUE! | -31370 | #VALUE!
x | Readers Branch | 3 | 07 | Carlisle | 10 - Traditional | SPEC | Y.Wang | #VALUE! | 2020-08-13 | 300 |  | 08/13/2020 | #VALUE! | 08/28/2020 |  |  | #VALUE! |  |  | #VALUE! | 08/30/2020 | 09/04/2020 | 2020-09-07 |  |  | #VALUE! | 12 | 0 | #VALUE! | 5 | #VALUE!
x | McRae & Lacy | 1 | 003 | Laurel | —— | SPEC | Y.Wang | #VALUE! | 2020-04-22 | 240 |  | 10/07/2019 | #VALUE! | 12/11/2019 |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 48 | 0 | #VALUE! | 0 | #VALUE!
x | McRae & Lacy | 1 | 004 | Davenport | —— | SPEC | Y.Wang | #VALUE! | 2020-04-22 | 240 |  | 10/07/2019 | #VALUE! | 12/11/2019 |  |  | #VALUE! |  |  | #VALUE! |  |  | 1900-01-01 |  |  | #VALUE! | 48 | 0 | #VALUE! | 0 | #VALUE!
x | Lauradell | 1 | 62 | Hadley | 25 - Folk Victorian | SPEC | Y.Wang | #VALUE! | 2020-07-20 | 220 |  | 07/20/2020 | #VALUE! | 07/23/2020 |  |  | #VALUE! |  |  | #VALUE! | 07/19/2020 | 08/19/2020 | 2020-08-20 |  |  | #VALUE! | 4 | 0 | #VALUE! | 23 | #VALUE!
x | Lauradell | 1 | 75 | Savannah | A - Folk Victorian | SPEC | C.Zobel | #VALUE! | 2020-07-24 | 300 |  | 07/27/2020 | #VALUE! | 08/05/2020 |  |  | #VALUE! |  |  | #VALUE! | 08/05/2020 | 10/21/2020 | 2020-10-22 |  | custom 1st floor, screened raised patio, custom 2nd floor, garage extension | #VALUE! | 8 | 0 | #VALUE! | 56 | #VALUE!
x | Harpers Mill | 4 | 29 | Carlisle | 10 - Traditional | SPEC | C.Zobel | #VALUE! | 2020-08-11 | 120 |  | 08/11/2020 | #VALUE! | 08/17/2020 |  |  | #VALUE! |  |  | #VALUE! | 08/21/2020 | 09/30/2020 | 2020-10-01 |  |  | #VALUE! | 5 | 0 | #VALUE! | 29 | #VALUE!
x | Culpepper Landing | 5 | 783 | Hickory | 30 - Craftsman | SPEC | C.Zobel | #VALUE! | 2020-08-19 | 180 |  | 08/19/2020 | #VALUE! | 09/11/2020 |  |  | #VALUE! |  |  | #VALUE! | 09/30/2020 | 10/28/2020 | 2020-10-29 |  |  | #VALUE! | 18 | 0 | #VALUE! | 21 | #VALUE!
x | Cypress Creek | 00 | 271 | Hartford Terrace | 40 - European | SPEC | C.Zobel | #VALUE! | 2020-09-02 | 240 |  | 09/03/2020 | #VALUE! | 10/06/2020 |  |  | #VALUE! |  |  | #VALUE! | 10/12/2020 | 01/26/2021 | 2021-01-27 |  |  | #VALUE! | 24 | 0 | #VALUE! | 77 | #VALUE!
x | Lake Margaret | 1 | 9 | Hartford II | B - Craftsman | SPEC | C.Zobel | #VALUE! | 10/29/2020 | 300 |  | 10/30/2020 | #VALUE! | 11/03/2020 |  |  | #VALUE! |  |  | #VALUE! | 11/03/2020 | 02/12/2021 | 2021-02-15 |  |  | #VALUE! | 3 | 0 | #VALUE! | 74 | #VALUE!
x | John Rolfe Square | 1 | 22 | Linden III | 10 - Traditional | SPEC | C.Zobel | #VALUE! | 11/07/2020 | 640 |  | 11/11/2020 | #VALUE! | 11/16/2020 |  |  | #VALUE! |  |  | #VALUE! | 12/03/2020 | 01/06/2021 | 2021-01-07 |  | w/ LTX basement | #VALUE! | 4 | 0 | #VALUE! | 25 | #VALUE!
x | Harpers Mill | 4 | 12 | Hartford II | BSE - Arts & Crafts | SPEC | C.Zobel | #VALUE! | 01/04/2021 | 180 |  | 01/05/2021 | #VALUE! | 01/08/2021 |  |  | #VALUE! |  |  | #VALUE! | 01/08/2021 | 02/01/2021 | 2021-02-02 |  |  | #VALUE! | 4 | 0 | #VALUE! | 17 | #VALUE!
x | Parkside Village | 4 | 23 | Hartford II | BSE - Arts & Crafts | SPEC | C.Zobel | #VALUE! | 01/05/2021 | 120 |  | 01/05/2021 | #VALUE! | 01/13/2021 |  |  | #VALUE! |  |  | #VALUE! | 01/14/2021 | 02/04/2021 | 2021-02-05 |  |  | #VALUE! | 7 | 0 | #VALUE! | 16 | #VALUE!
x | The Parke @ Cypress Creek | 1 | 67 | Acton | 40 - New England | SPEC | C.Zobel | #VALUE! | 02/01/2021 | 240 |  | 02/02/2021 | #VALUE! | 02/22/2021 |  |  | #VALUE! |  |  | #VALUE! | 03/01/2021 | 04/12/2021 | 2021-04-13 |  |  | #VALUE! | 15 | 0 | #VALUE! | 31 | #VALUE!
x | Cypress Creek | 7C | 365 | Linden III | 25 - Folk Victorian | SPEC | C.Zobel | #VALUE! | 02/09/2021 | 300 |  | 02/10/2021 | #VALUE! | 02/22/2021 |  |  | #VALUE! |  |  | #VALUE! | 02/25/2021 | 04/12/2021 | 2021-04-13 |  |  | #VALUE! | 9 | 0 | #VALUE! | 33 | #VALUE!
x | Lauradell | 1 | 44 | Grayson | 10 - Traditional | SPEC | C.Zobel | #VALUE! | 02/26/2021 | 480 |  | 03/01/2021 | #VALUE! | 03/04/2021 |  |  | #VALUE! |  |  | #VALUE! | 03/08/2021 | 04/02/2021 | 2021-04-05 |  |  | #VALUE! | 4 | 0 | #VALUE! | 20 | #VALUE!
x | Parkside Village | 4 | 13 | Fulton | B - Folk Victorian | SPEC | C.Zobel | #VALUE! | 03/17/2021 | 180 |  | 03/18/2021 | #VALUE! | 03/25/2021 |  |  | #VALUE! |  |  | #VALUE! | 04/19/2021 | 05/17/2021 | 2021-05-18 |  |  | #VALUE! | 6 | 0 | #VALUE! | 21 | #VALUE!
x | Cypress Creek | 7B | 323 | Linden III | 25 - Folk Victorian | SPEC | C.Zobel | #VALUE! | 04/06/2021 | 240 |  | 04/07/2021 | #VALUE! | 05/13/2021 |  |  | #VALUE! |  |  | #VALUE! | 05/17/2021 | 07/01/2021 | 2021-07-02 |  |  | #VALUE! | 27 | 0 | #VALUE! | 34 | #VALUE!
x | The Parke @ Cypress Creek | 1 | 113 | Corvallis | 30 - Craftsman | SPEC | C.Zobel | #VALUE! | 05/06/2021 | 300 |  | 05/07/2021 | #VALUE! | 06/04/2021 |  |  | #VALUE! |  |  | #VALUE! | 06/07/2021 | 07/01/2021 | 2021-07-02 |  |  | #VALUE! | 21 | 0 | #VALUE! | 19 | #VALUE!
x | Readers Branch | 2 | 19 | Fulton Terrace | A - Colonial | SPEC | C.Zobel | #VALUE! | 05/28/2021 | 240 |  | 06/01/2021 | #VALUE! | 06/09/2021 |  |  | #VALUE! |  |  | #VALUE! | 06/14/2021 | 07/13/2021 | 2021-07-14 |  |  | #VALUE! | 7 | 0 | #VALUE! | 22 | #VALUE!
x | Lauradell | 1 | 137 | Grayson | 10 - Traditional | SPEC | C.Zobel | #VALUE! | 06/02/2021 | 0 |  | 06/02/2021 | #VALUE! | 06/07/2021 |  |  | #VALUE! |  |  | #VALUE! | 06/04/2021 | 06/22/2021 | 2021-06-23 |  |  | #VALUE! | 4 | 0 | #VALUE! | 13 | #VALUE!
x | Readers Branch | 2 | 20 | Belmont Terrace | 10 - Traditional | SPEC | C.Zobel | #VALUE! | 06/03/2021 | 480 |  | 06/04/2021 | #VALUE! | 06/16/2021 |  |  | #VALUE! |  |  | #VALUE! | 06/17/2021 | 07/13/2021 | 2021-07-14 |  |  | #VALUE! | 9 | 0 | #VALUE! | 19 | #VALUE!
x | Cypress Creek | 7B | 321 | Carlisle | 15 - Arts & Crafts | SPEC | C.Zobel | #VALUE! | 08/18/2021 | 300 |  | 08/19/2021 | #VALUE! | 09/02/2021 |  |  | #VALUE! |  |  | #VALUE! | 09/09/2021 | 10/13/2021 | 2021-10-14 |  |  | #VALUE! | 11 | 0 | #VALUE! | 25 | #VALUE!
x | Readers Branch | 3 | 58 | Fulton | A - Colonial | SPEC | C.Zobel | #VALUE! | 01/17/2021 | 180 |  | 01/18/2021 | #VALUE! | 01/20/2021 |  |  | #VALUE! |  |  | #VALUE! | 01/25/2021 | 03/01/2021 | 2021-03-02 |  |  | #VALUE! | 3 | 0 | #VALUE! | 26 | #VALUE!
x | Lauradell | 1 | 26 | Raleigh | 20 - Arts & Crafts A | SPEC | C.Zobel | #VALUE! | 09/20/2021 | 300 |  | 09/21/2021 | #VALUE! | 09/27/2021 |  |  | #VALUE! |  |  | #VALUE! | 10/05/2021 | 11/08/2021 | 2021-11-09 |  | attic above garage | #VALUE! | 5 | 0 | #VALUE! | 25 | #VALUE!
x | Readers Branch | 3 | 8 | Fulton | B - Folk Victorian | SPEC | C.Zobel | #VALUE! | 05/26/2021 | 30 |  | 05/26/2021 | #VALUE! | 05/28/2021 |  |  | #VALUE! |  |  | #VALUE! | 06/01/2021 | 06/28/2021 | 2021-06-29 |  |  | #VALUE! | 3 | 0 | #VALUE! | 20 | #VALUE!
x | Fox Creek |  | 3 | Claremont |  |  | R.Arias | 1900-01-02 | 2019-01-02 |  |  | 03/18/2020 | 1900-01-16 |  |  |  | 1900-01-16 |  |  | 1900-01-19 |  |  | 1900-01-01 |  |  | 31047 | -31363 | 0 | -1 | 0 | 0
x | Cypress Creek |  | 347 | Westminster |  |  | R.Arias | 1900-01-02 | 2019-01-03 |  |  |  | 1900-01-16 |  |  |  | 1900-01-16 |  |  | 1900-01-19 |  |  | 1900-01-01 |  |  | 31048 | 0 | 0 | -1 | 0 | 0
x | Lauradell | 1 | 86 | Newport |  |  | R.Arias | 1900-01-02 | 2019-01-04 |  |  |  | 1900-01-16 |  |  |  | 1900-01-16 |  |  | 1900-01-19 |  |  | 1900-01-01 |  |  | 31049 | 0 | 0 | -1 | 0 | 0
x | Lauradell | 1 | 66 | Manchester |  |  | R.Arias | 1900-01-02 | 2019-01-05 |  |  |  | 1900-01-16 |  |  |  | 1900-01-16 |  |  | 1900-01-19 |  |  | 1900-01-01 |  |  | 31049 | 0 | 0 | -1 | 0 | 0
x | Lauradell | 1 | 70 | Manchester |  |  | R.Arias | 1900-01-02 | 2019-01-08 |  |  |  | 1900-01-16 |  |  |  | 1900-01-16 |  |  | 1900-01-19 |  |  | 1900-01-01 |  |  | 31051 | 0 | 0 | -1 | 0 | 0
x | Readers Branch | 1 | 007 | Linden Terrace | 10 - Traditional |  |  | 1900-01-02 | 2019-05-13 |  |  | 08/05/2019 | 1900-01-16 | 08/14/2019 |  |  | 1900-01-16 |  |  | 1900-01-19 | 08/15/2019 | 09/06/2019 | 2019-09-09 |  |  | 31140 | 8 | 0 | 31208 | 17 | 31225
x | Readers Branch | 2 | 23 | Belmont | 30 - Craftsman |  | R.Arias | 1900-01-02 | 2020-01-14 | 380 |  | 01/15/2020 | 1900-01-16 | 01/21/2020 |  |  | 1900-01-16 |  |  | 1900-01-19 | 01/21/2020 | 02/19/2020 | 2020-02-20 |  |  | 31316 | 5 | 0 | 31321 | 22 | 31343
x | Cypress Creek | 00 | 71 | Westminster | B - Craftsman |  | R.Arias | 1900-01-02 | 2020-02-17 | 210 |  | 02/17/2020 | 1900-01-16 |  |  |  | 1900-01-16 |  |  | 1900-01-19 |  |  | 1900-01-01 |  |  | 31340 | -31341 | 0 | -1 | 0 | 0
x | Cypress Creek | 7C | 354 | Westminster | B - Craftsman |  | R.Arias | 1900-01-02 | 2020-02-19 | 200 |  | 02/19/2020 | 1900-01-16 |  |  |  | 1900-01-16 |  |  | 1900-01-19 |  |  | 1900-01-01 |  |  | 31342 | -31343 | 0 | -1 | 0 | 0
[8 empty] | 1900-01-02 |  |  |  |  | 1900-01-16 |  |  |  | 1900-01-16 |  |  | 1900-01-19 |  |  | 1900-01-01 |  |  | -1 | 0 | 0 | -1 | 0 | 0
[8 empty] | 1900-01-02 |  |  |  |  | 1900-01-16 |  |  |  | 1900-01-16 |  |  | 1900-01-19 |  |  | 1900-01-01 |  |  | -1 | 0 | 0 | -1 | 0 | 0
[8 empty] | 1900-01-02 |  |  |  |  | 1900-01-16 |  |  |  | 1900-01-16 |  |  | 1900-01-19 |  |  | 1900-01-01 |  |  | -1 | 0 | 0 | -1 | 0 | 0
[8 empty] | 1900-01-02 |  |  |  |  | 1900-01-16 |  |  |  | 1900-01-16 |  |  | 1900-01-19 |  |  | 1900-01-01 |  |  | -1 | 0 | 0 | -1 | 0 | 0
[8 empty] | 1900-01-02 |  |  |  |  | 1900-01-16 |  |  |  | 1900-01-16 |  |  | 1900-01-19 |  |  | 1900-01-01 |  |  | -1 | 0 | 0 | -1 | 0 | 0
[8 empty] | 1900-01-02 |  |  |  |  | 1900-01-16 |  |  |  | 1900-01-16 |  |  | 1900-01-19 |  |  | 1900-01-01 |  |  | -1 | 0 | 0 | -1 | 0 | 0
[8 empty] | 1900-01-02 |  |  |  |  | 1900-01-16 |  |  |  | 1900-01-16 |  |  | 1900-01-19 |  |  | 1900-01-01 |  |  | -1 | 0 | 0 | -1 | 0 | 0
Formulas:
Draft Deadline = WORKDAY(LotTracker[[#This Row],[Contract Date]],2,)
Planned Receipt = WORKDAY(LotTracker[[#This Row],[Draft Deadline]],10,)
Planned Receipt2 = WORKDAY(LotTracker[[#This Row],[Draft Deadline]],10,)
Planned Submit = WORKDAY(LotTracker[[#This Row],[Planned Receipt]],3,)
BBP = WORKDAY(LotTracker[[#This Row],[RECEIVED]],1)
Cycle times = NETWORKDAYS(LotTracker[[#This Row],[Contract Date]],LotTracker[[#This Row],[Actual]])-1
Engineer = NETWORKDAYS(LotTracker[[#This Row],[Eng. Sent]],LotTracker[[#This Row],[Actual Receipt]])
Plat = NETWORKDAYS(LotTracker[[#This Row],[Plat Sent]],LotTracker[[#This Row],[Actual Receipt2]])
Contract--Permit Submission = NETWORKDAYS(LotTracker[[#This Row],[Contract Date]],LotTracker[[#This Row],[Actual Submit]])-1
Permit Processing = NETWORKDAYS(LotTracker[[#This Row],[Actual Submit]],LotTracker[[#This Row],[RECEIVED]])
Total Pre-Con = NETWORKDAYS(LotTracker[[#This Row],[Contract Date]],LotTracker[[#This Row],[RECEIVED]])

## DATA
Team Member | Community | Products | Elevations | Eng | Plat | Jurisdiction
N.Blinn | Greengate | Belmont | Traditional | HBS | Bolen | Blacksburg
R.Arias | Harpers Mill | Belmont Terrace | Arts & Crafts | Riverside | Koontz | Chesterfield
Y.Wang | John Rolfe Square | Grayson | Folk Victorian | Struc Tech | Parker | Christiansburg
B.James | Lauradell | Hartford Terrace | Craftsman | DFI | Hassel | Goochland
C.Zobel | Readers Branch | Helena | European |  | Cardinal | Hanover
| Manchester | Linden Terrace | Arts & Crafts B |  |  | Henrico
| WBV - East | Malvern | Colonial |  |  | Isle of Wight
| McRae & Lacy | Park |  |  |  | Richmond
| Cypress Creek | Raleigh
| Parkside Village | Rowland | QA-A-1-F
| Lake Margaret | Westmoreland | QA-A-1-R
| Fox Creek | Southaven | QA-A-2-F
| Culpepper Landing | Laurel | QA-A-2-R
| Ford's Colony | Davenport | QA-B-1-F
| Givens Farm | Corvallis | QA-B-1-R
| The Parke @ Cypress Creek | Beverly | QA-B-2-F
| Lankford Crossing | Hadley | QA-B-2-R
| Ginter Park | Linden III | QA-C-1-F
| The Meadows | Hartford II | QA-C-1-R
| Row at Westhampton | Carlisle | QA-C-2-F
|  | Fulton | QA-C-2-R
|  | Westminster | QA-D-1-F
|  | Newport | QA-D-1-R
|  | Manchester | QA-D-2-F
|  | Claremont | QA-D-2-R
|  | Wellesley | QA-E-1-F
|  | Fulton Terrace | QA-E-1-R
|  | Savannah | QA-E-2-F
|  | Hickory | QA-E-2-R
|  | Easton | GE-A-1-F
|  | Stamford | GE-A-1-R
|  | Acton | GE-A-2-F
|  | Bradford | GE-A-2-R
|  | Westfield | GE-B-1-F
|  | Hawthorne | GE-B-1-R
|  | Caroline | GE-B-2-F
|  | Wellington II | GE-B-2-R
GE-C-1-F
GE-C-1-R
GE-C-2-F
GE-C-2-R
GE-D-1-F
GE-D-1-R
GE-D-2-F
GE-D-2-R
GR-A-1-F
GR-A-1-R
GR-A-2-F
GR-A-2-R
GR-B-1-F
GR-B-1-R
GR-B-2-F
GR-B-2-R
GR-C-1-F
GR-C-1-R
GR-C-2-F
GR-C-2-R
GR-D-1-F
GR-D-1-R
GR-D-2-F
GR-D-2-R